## Feuil1
| JASIC | IDIADA | UTAC | CATARC | TUV | BS | CON | GY | MI | PI | HK | NOK | ITMA | SRI
General status | testing activities can operate | Open, testing activities | is open, work on wet grip, test activities are still open | all test can be performed | testing acivities are operational, actually wet grip track is closed and intended to be reopened in May. | see document WT-10-06 | see document WT-10-06 | see document WT-10-06 | see document WT-10-06 | see document WT-10-06 | see document WT-10-06 | see document WT-10-06
testing at different times | Testing activities can operate now, 3PMSF tyres staring in October. | possible to receive the tyres in different batches. Expectation to start in June and in September for 3PMSF tyres | prefer testing in 1 batch. Testing can start mid July. 3PMSF tyre to be tested in September. | prefer testing in 1 batch, sevral tyres have been received. Prefer to have received all tyres in order to test in one batch. | TUV: can split in 2 sessions, and is able to test 14 tyres (50%) in June; HK: tbc, but natural division of the test is ok as Normal and Winter tyres will not be tested i the same test session | not applicable | not applicable
tyre reception ability | BS, MI, ITMA (1 worng received tyre and 1 sepc is missing)). Still need to receive from Conti, Goodyear and Pi | yes | yes | BS, JASIC, ITMA, MI, NOK, HK. Not received: CONTI, GY. | yes | Tyre received from MI, ITMA,HK, Jasic. Waiting 12 tyres from GY, CON and SRI | warehouse is open. Majority of the tyres arrived | Nokian tyres received, other tyres to be confirmed | BS, HK, Jasic, NOK, SRI ITMA. Not received CON, GY and PI | tyres can be received from now on teh new address communicated | from JASIC, other tyres to be received | waiting on MES tyres | not applicable | not applicable
tyre send out ability | All Jasic tyres have been sent out, All tyres received except from PI |  |  | Conti tyres to be received, SRTT still not received (customs issues). Pirelli received |  | all tyres shipped to all | All shipments are sent out | All tyres have been sent out | all tyres have been sent out | Tyres are underway to be delivered. Some delay for JASIC and CATARC | completed | completed | Conti, M, BS, MES, JASIC + Catarc and Goodyear are shipped | Tyres have been delivered, except CATARC (info 5 July)
Staring buffing | Own tyres will be buffed begin of July waiting to buff GY, CONTI an PI when arrived |  |  | 4 to 5 tyres buffing capacity/day. End of buffing will comply with IWG timeline (End of December) |  | all tyres are arrived, buffing started mid October, and intend to be completed begin November | All tyres were received, and buffing ongoing (about 50% done) | 5 tyres still to be buffed. 21 tyres are already buffed | all tyres are buffed (473 tyres) | 9 buffed tyres next week, rest of tyres buffed end of November
Sending of buffed tyres | All Jasic tyres have been sent out | All the tyres received | Tyres received | missing tyres: 5 tyres (SRI) | TUV: all tyres received, except starmaxx that will be disregarded as nopt available; MI: Completed; HK: Tyres received; NOK: All tyres received
start testing | starts in last week of October and intend to finish by end of November | starting started begin September. Target is to finish in October begin November(5 blocks left of the test) | tests have started, intention is to finish by end of November | Testing targeting to start in November/December | half of the batch is tested, remaining tests to be performed by end 2020 | Mid or End of November | plan to start testing in Q4 | November | All trailer test done (except 2 tyres). Vehicle test in November | November (1st group of tyres) | November | started in August and is ongoing, supposed to be finished by November