## Slide 1: Drafting DCAS UN Regulation
Progress report to the 10th ADAS TF Session
TF on ADAS Leadership ADAS-10-06

## Slide 2: Status
As there is no drafting group, the ADAS TF Leadership itself takes care of the drafting process.
The Leadership reports limited progress in drafting, which was however restrained by lack of time.
The current version of the Master Document is ADAS-10-02.

## Slide 3: Progress outline
The drafting work plan after the 9th ADAS TF session and the status of work
Integrate the comments from the minutes of the 8th ADAS TF meeting (ADAS-08-10) into the latest masted document (ADAS-09-05); Done
Treat the same way the minutes of the 9th ADAS TF meeting (ADAS-09-10); Done
Check in the master document, if it addresses already the regulatory items from the presentation ADAS-09-09, slide 13. If not, include placeholders; Partially done, did not yet integrate ISO 26262/21448, risk management, traffic situation response.
Convert the comments in the master document to the regulatory test or placeholders; Done partly. Have not changed testing provisions.
For the additional possible regulatory items, carry out risk analysis per ISO 26262 + ISO 21448. Not yet done.
Consider restructuring of the Specifications to bring the driver engagement, HMI and driver information sections closer together or possibly integrate them into one Chapter to reflect on some common concerns. Not yet done.
Some fundamental additions have been made to the driver engagement section in order to facilitate discussion and make progress.

## Slide 4: The outcome of the 9th ADAS TF session to be addressed in drafting
(ITU) with reference to the discussion regarding statistics and accidentology, to introduce requirements on the manufacturer to report on the amount of driving under the system, the number of accidents that have occurred, crash-related events etc. → Perhaps, this cannot be done at the type approval process, but relevant for the lifetime operation monitoring.
(Norway, Finland) to propose a driver’s license for assistance systems; whether we have any knowledge on the actual driver competence when the system is being used. → Forward the proposal to WP.1.
(Chair) the systems as outlined in the use case document (ADAS-08-06) should be considered as DCAS provided that appropriate driver engagement is maintained.
(Chair) the safeguard clause is that the system should be deactivated if it is not capable of operating in a given environment. → The system boundaries will need to be defined properly.
(Sweden) whether a system is considered as ADS or assistance system depends on the system functionality. → We still need to outline criteria which would differentiate a DCAS from an ADS, noting that the main argument of industry is that a system is assisted if it requires continued engagement of the driver. The control strategy will need to be defined (how the system assists the driver).

## Slide 5: The outcome of the 9th ADAS TF session to be addressed in drafting
(OICA-CLEPA), as a way forward, to proceed with the listed ‘use cases’ and to subsequently discuss what would be needed to have stakeholders be comfortable in order to permit such systems, specifying what would be needed for OEDR, driver engagement and other elements. → Go ahead with this approach.
(Chair, the Netherlands) not only driver’s visual engagement but also mental engagement may be required for safe operation. → (Co-Chair) it may not be appropriate to specify monitoring technologies but rather to specify how long the driver may be disengaged. There should be limits to disengagement from the driver task. The driver engagement could mean to include positive actions from the driver to the DCAS, steering or brake pedal as well as monitoring that the driver is looking at the road conditions. To outline what we mean by driver engagement and outline what is expected of the driver. How would industry ensure driver engagement for different use cases?
(Chair) DCAS should be able to initiate maneuvers itself. → A control strategy may need to be described indicating that the driver and system work in conjunction, reducing workload from the driver. What requirements are necessary to ensure safety with system-initiated maneuvers. Clear notice in sufficient time will have to be provided by systems.

## Slide 6: Thank you for your attention!