## Full List
Outcome | Step | Forum | Forum ID | Date | Location | Further description of outcome or step | UN wiki
DEOP status report | Approved | GRSP | 72 | 2022-12-05 | Geneva | Written DEOP status report and a draft proposal as a basis to discuss the next step. | GRSP-72-10e.pdf
DEOP status report | Approved | GRSP | 72 | 2022-12-05 | Geneva | PPT version of the DEOP status report. | PowerPoint-presentation
Terms of reference IWG EqOP | Approved | GRSP | 72 | 2022-12-05 | Geneva | The ToR was drafted in a separate document and presented at the GRSP-72. | GRSP-72-45r1e (4).pdf
Terms of reference IWG EqOP | Discussed | IWG | 1 | 2023-04-06 | Yokohama | The ToR was used in the first meeting to start the IWG EqOP. | EqOP 1st session - Transport - Vehicle Regulations - UNECE Wiki
Report to GRSP-73 from IWG | Presented | GRSP | 73 | 2023-05-15 | Geneva | Included a presentation of the workplan and worktable. | Equitable Occupant Protection - EqOP
GRSP-73 Report | Approved | GRSP | 73 | 2023-05-15 | Geneva | Agenda item 20 of the formal GRSP report. | ECE-TRANS-WP.29-GRSP-73e.pdf
Workplan and worktable | Agreed | IWG | 2 | 2023-05-15 | Geneva | The worktable is an overview of the key research studies identified by the IWG EqOP. | EqOP 2nd session - Transport - Vehicle Regulations - UNECE Wiki
Field data | Agreed | Workshop | 1 | 2023-09-05 | Cologne | Field data of soft-tissue neck injuries in rear-end impacts shows that women are at higher risk for permanent medical impairment. | EqOP 1st workshop - Transport - Vehicle Regulations - UNECE Wiki
CLEPA R17 proposal | Agreed | Workshop | 1 | 2023-09-05 | Cologne | Agreed to proceed with the proposal. | EqOP 1st workshop - Transport - Vehicle Regulations - UNECE Wiki
Updated worktable | Discussed | IWG | 3 | 2023-09-21 | On-line | We agreed to see the table as “work in progress”. The table will be the basis for workshop in Brussels. | EqOP 3rd session - Transport - Vehicle Regulations - UNECE Wiki
Task forces as a structure of the IWG | Agreed | Workshop | 2 | 2023-10-24 | Brussels | Decided to proceed the work in 5 Task Forces. | EqOP 2nd workshop - Transport - Vehicle Regulations - UNECE Wiki
Equity issues and research gaps | Agreed | Workshop | 2 | 2023-10-24 | Brussels | Agreement regarding equity issues and research gaps, respectively. | EqOP 2nd workshop - Transport - Vehicle Regulations - UNECE Wiki
Worktable and Task Forces | Agreed | Workshop | 2 | 2023-11-06 | On-line | One task force shall write a report based on the worktable content. | EqOP 2nd workshop, follow-up meeting - Transport - Vehicle Regulations - UNECE Wiki
"5Ws" (and how…) regarding Virtual Testing | Presented | Workshop | 3 | 2023-11-14 | Munich | Presentations by several participants followed by joint discussion and break-out sessions in smaller groups. REMARK: THIS IN-PERSON WORKSHOP WAS ALSO THE FIRST MEETING OF TF3. | EqOP 3rd workshop - Transport - Vehicle Regulations - UNECE Wiki
Motivation for VT (ultimately with HBM) | Agreed | Workshop | 3 | 2023-11-14 | Munich | More robust evaluation considering human diversity and different load cases; faster type-approval process, etc. | EqOP 3rd workshop - Transport - Vehicle Regulations - UNECE Wiki
VCT in type-approval regulations | Discussed | Workshop | 3 | 2023-11-14 | Munich | Application of the framework type-approval regulation (2018/858 Annex VIII), or VT as outlined directly by the regulation in point. | EqOP 3rd workshop - Transport - Vehicle Regulations - UNECE Wiki
VCT in type-approval regulations | Discussed | Workshop | 3 | 2023-11-14 | Munich | In practice, applied in two ways: 1) a relative approach to determine worst-case cases, or 2) to replace physical testing. | EqOP 3rd workshop - Transport - Vehicle Regulations - UNECE Wiki
Potential barriers | Agreed | Workshop | 3 | 2023-11-14 | Munich | Trust in methods and processes, IP issues, traceability of results, knowledge gaps, storage of data for independent checking. | EqOP 3rd workshop - Transport - Vehicle Regulations - UNECE Wiki
Identification of building blocks for VCT | Agreed | Workshop | 3 | 2023-11-14 | Munich | Building blocks: Occupant model, car model, FE software, Validation Process, a first discussion on requirements for virtual crash testing in the contracting parties‘ view. | EqOP 3rd workshop - Transport - Vehicle Regulations - UNECE Wiki
Identification of building blocks for VCT | Agreed | Workshop | 3 | 2023-11-14 | Munich | Agreement on requirements for virtual crash testing in the contracting parties‘ view highlighting that a VT procedure needs to include testable conditions for CoP tests and independent checking. | EqOP 3rd workshop - Transport - Vehicle Regulations - UNECE Wiki
Draft report to GRSP-74 from IWG | Agreed | IWG | 4 | 2023-11-22 | On-line | In addition, a decision that the worktable is ready to be posted on the UN wiki. | EqOP 4th session - Transport - Vehicle Regulations - UNECE Wiki
Report to GRSP-74 from IWG | Presented | GRSP | 74 | 2023-12-04 | Geneva | Contained conclusions from all of the workshops in 2023 and an updated workplan with task forces, and the EqOP approach. | Equitable Occupant Protection, report to the 74th session of GRSP
Proposal to update headrest regulations | Presented | GRSP | 74 | 2023-12-04 | Geneva | Inf EqOP - WHIPLASH improvements for small occupants. | PowerPoint Presentation
GRSP-74 Report | Agreed | GRSP | 74 | 2023-12-04 | Geneva | Agenda item 17 of the formal GRSP report (included also a recognition of the preliminary CLEPA proposal). | ECE-TRANS-WP.29-GRSP-74e.pdf
"5Ws" (and how…) - continued | Discussed | TF3 | 2 | 2024-01-31 | On-line | Further presentations, including an overview of current related VCT activities. | 2nd meeting/workshop TF3 - Transport - Vehicle Regulations - UNECE Wiki
Process building blocks for VCT | Agreed | TF3 | 2 | 2024-01-31 | On-line | Building blocks defined to structure discussion of next steps: Simulation Software, Models of occupant, Models of car (components), Virtual testing load cases, Virtual testing results, Checking Methods | 2nd meeting/workshop TF3 - Transport - Vehicle Regulations - UNECE Wiki
Requirements for VCT (Virtual Crash Testing) | Discussed | TF3 | 2 | 2024-01-31 | On-line | Requirements (reproducibilty, repeatability, traceability, avoid manipulations, physical testable validations, ensure protection against loss of health and life of diverse occupants) and possible approaches to address the requirements were sketched based on these initial discussion on requirements | 2nd meeting/workshop TF3 - Transport - Vehicle Regulations - UNECE Wiki
Status report from task forces | Agreed | IWG | 5 | 2024-02-07 | On-line | A specific brief of the 2nd meeting of TF3 (VCT) was given. Meeting participants also encouraged to actively participate in the task forces. | EqOP IWG 5th session - Transport - Vehicle Regulations - UNECE Wiki
Status of SETs (Seat Evaluation Tools) | Presented | TF2 | 1 | 2024-02-20 | On-line | Prof Linder presented preliminary test results of the SETs from 2023; Injury criteria for the SET’s remains to be defined. | 1st meeting TF2 - Transport - Vehicle Regulations - UNECE Wiki
CLEPA R17 proposal | Discussed | TF2 | 1 | 2024-02-20 | On-line | The CLEPA draft proposal for a regulatory change with focus on the headrest was presented and discussed. | 1st meeting TF2 - Transport - Vehicle Regulations - UNECE Wiki
NL proposal on R17 | Discussed | TF2 | 2 | 2024-03-18 | On-line | Only one agenda point, namely the NL proposal; CLEPA has a concern about unknown side effect of the NL proposal; adjourn. | 2nd meeting TF2 - Transport - Vehicle Regulations - UNECE Wiki
Aim for a peer-reviewed report of the worktable | Agreed | TF1 | 1 | 2024-03-21 | On-line | The TF1 shall not perform research, it shall review the literature as in the worktable, i.e. put the worktable into a written format. | 1st meeting TF1 - Transport - Vehicle Regulations - UNECE Wiki
Four different approaches | Discussed | TF3 | 3 | 2024-04-12 | On-line | Four approaches (concepts for virtual testing procedures) were sketched which fulfill the previously defined requirements including either generic of IP protected vehicle models and simulations performed either at authorities or at VMs | 3rd meeting/workshop TF3 - Transport - Vehicle Regulations - UNECE Wiki
Use digital real vehicle models | Agreed | TF3 | 3 | 2024-04-12 | On-line | Agreement to proceed with 1&2, both using OEM vehicle models where simulation are either performed at the VM or at authority - after discussion about the pros&cons of the four different approaches - the idea using generic vehicle models was discarded | 3rd meeting/workshop TF3 - Transport - Vehicle Regulations - UNECE Wiki
Credibility assessment of virtual testing | Presented | TF3 | 3 | 2024-04-12 | On-line | UTAC presented the ADAD & ADS approach for virtual testing (where not all conditions are physical testable). | 3rd meeting/workshop TF3 - Transport - Vehicle Regulations - UNECE Wiki
Aim for an integrated report, not study-for-study | Agreed | TF1 | 2 | 2024-04-18 | On-line | Also consider new studies, being published, and for this reason we should update the worktable accordingly. | 2nd meeting TF1 - Transport - Vehicle Regulations - UNECE Wiki
Status report from task forces | Agreed | IWG | 6 | 2024-05-15 | On-line | Decision to make a short report to GRSP based on TF statuses. In addition, the WP6 Guidelines on Developing Gender-responsive Standards were presented. | EqOP IWG 6th session - Transport - Vehicle Regulations - UNECE Wiki
Load case independent requirements | Discussed | TF3 | 4 | 2024-05-17 | On-line | Generic loadcase independent requirements were discussed including model and simulation management, model requirements, model / simulation software verification, model validation process. Further definitions and requirements will depend on the type of load case and assessment. | 4th meeting/workshop TF3 - Transport - Vehicle Regulations - UNECE Wiki
Load case selection | Agreed | TF3 | 4 | 2024-05-17 | On-line | Conclusion that VCT procedure shall have a real-world benefit in the terms of EqOP. | 4th meeting/workshop TF3 - Transport - Vehicle Regulations - UNECE Wiki
NL proposal on R17 | Discussed | TF2 | 3 | 2024-05-22 | On-line | The chair stated that the NL proposal was seen as sprung out of the EqOP work despite lack of a complete support, to be noted at GRSP. | 3rd meeting TF2 - Transport - Vehicle Regulations - UNECE Wiki
Agenda for TF2 workshop in Stockholm | Agreed | TF2 | 3 | 2024-05-22 | On-line | Also decision to have ad hoc meetings to prepare for the workshop in Stockholm. | 3rd meeting TF2 - Transport - Vehicle Regulations - UNECE Wiki
Report to GRSP-75 from IWG | Presented | GRSP | 75 | 2024-05-27 | Geneva | The report provided the TF statuses and also mentioned details of the upcoming meetings in Stockholm. | Equitable Occupant Protection, drafted report to the 75th session of GRSP
GRSP-75 Report | Agreed | GRSP | 75 | 2024-05-27 | Geneva | USA requested that the IWG EqOP should report to WP29 as the task of the IWG EqOP is monumental. | ECE-TRANS-WP.29-GRSP-75e.pdf
CLEPA R17 proposal (GRSP-75-30) | Agreed | GRSP | 75 | 2024-05-27 | Geneva | GRSP agreed to send GRSP-75-30, tabled by the expert from CLEPA, to the IWG EqOP, and merged with GRSP/2024/15. | GRSP-75-30e.pdf | ECE-TRANS-WP.29-GRSP-2024-15e.pdf
NL proposal on R17 from 2023 | Withdrawn | GRSP | 75 | 2024-05-27 | Geneva | CLEPA presented a response to the NL proposal. | PowerPoint Presentation
CLEPA R17 proposal further refined | Agreed | TF2 | 3 | 2024-05-28 | On-line | A series of ad hoc meetings under TF2 until October 2024 to refine the CLEPA proposal up front GRSP-76. | Ad hoc meetings - Transport - Vehicle Regulations - UNECE Wiki
Intitial meeting to agree upon aim of TF5 | Agreed | TF5 | 1 | 2024-06-11 | On-line | Aim is to review assessment ideas for currently overlooked injuries (focusing equity issues, high frequency, and high risk of LTC). | 1st meeting TF5 - Transport - Vehicle Regulations - UNECE Wiki
Chair asked for relevant presentations | Discussed | TF5 | 1 | 2024-06-11 | On-line | Volunteers came forward on extremity, neck and brain injuries. TRL mentioned a review within ISO a few years ago, on biomechanical data for injury criteria, also when developing THOR and WSID. | 1st meeting TF5 - Transport - Vehicle Regulations - UNECE Wiki
GRSP chair had sought guidance from WP29 | Agreed | WP29 | 193 | 2024-06-25 | Geneva | Referred back to GRSP (WP29 referred the discussion on sequencing back to GRSP and the IWG on EqOP). | ECE-TRANS-WP.29-1179e.pdf
Load case selection | Agreed | TF3 | 5 | 2024-08-29 | On-line | Possible load-case candidates: frontal and rear impact, respectively, using HBM for assessment and ATD for validation. | 5th meeting/workshop TF3 - Transport - Vehicle Regulations - UNECE Wiki
Load case selection | Agreed | TF3 | 5 | 2024-08-29 | On-line | Use case should include (physically) testable conditions which can be the starting point of implementation, but are anyway needed for validation of simulation models and CoP testing. | 5th meeting/workshop TF3 - Transport - Vehicle Regulations - UNECE Wiki
GTR7 recap | Presented | TF2 | 4 | 2024-09-09 | Stockholm | Dr Lorenz provided an overview of the GTR7 development. | 4th meeting TF2 (In person Workshop) - Transport - Vehicle Regulations - UNECE Wiki
An approach to seatback load-taking evenness | Presented | TF2 | 4 | 2024-09-09 | Stockholm | Prof Jakobsson presented an approach to reduce the prevalence of soft tissue neck injuries in rear impacts. | 4th meeting TF2 (In person Workshop) - Transport - Vehicle Regulations - UNECE Wiki
Seatback energy and load management | Presented | TF2 | 4 | 2024-09-09 | Stockholm | Dr Edwards presented a study on high severity rear-end impact with pressure sensor analysis of interaction between occupant and seatback. | 4th meeting TF2 (In person Workshop) - Transport - Vehicle Regulations - UNECE Wiki
Whiplash tests using SET 50F and 50 M | Presented | TF2 | 4 | 2024-09-09 | Stockholm | Prof Linder presented results from testing of two seats, which have known risks from the field, with the SETs. | 4th meeting TF2 (In person Workshop) - Transport - Vehicle Regulations - UNECE Wiki
FE SET 50F and 50 M | Presented | TF2 | 4 | 2024-09-09 | Stockholm | Dr Jobin John presented the FE versions of the SETs, upon we discussed to use the rear-end impact sled test as a PoC of virtual crash testing. | 4th meeting TF2 (In person Workshop) - Transport - Vehicle Regulations - UNECE Wiki
Seatback energy management - conclusion | Agreed | TF2 | 4 | 2024-09-09 | Stockholm | Agreement that the whole seatback determines performance, i.e., the regulatory safety performance assessment should potentially address the whole seatback, including the headrest, as one entity | 4th meeting TF2 (In person Workshop) - Transport - Vehicle Regulations - UNECE Wiki
Report from the Task Forces | Agreed | IWG | 7 | 2024-09-10 | Stockholm | TF4 not yet started; potentially link TF4 to or merge with TF3, yet to be decided. | EqOP IWG 7th session - Transport - Vehicle Regulations - UNECE Wiki
Load case selection | Agreed | IWG | 7 | 2024-09-10 | Stockholm | Selection criteria for use case used for proof of concept of VCT: include testable (CoP) and non-testable (challenges for procedure) conditions, include HBMs (ToR), good predictability of simulation models, high reproducibilty of validation tests, address equity issue with high relevance (lead to more equitable occupant proetction) | EqOP IWG 7th session - Transport - Vehicle Regulations - UNECE Wiki
Purpose of PoC, Discussion in GRSP / WP.29 | Agreed | IWG | 7 | 2024-09-10 | Stockholm | Proof of concept as basis for decision making for GRSP / WP 29 how to proceed with virtual crash testing and on which level. | EqOP IWG 7th session - Transport - Vehicle Regulations - UNECE Wiki
Load case for proof of concept of VCT | Agreed | IWG | 7 | 2024-09-10 | Stockholm | Frontal load case for front row, BIW with focus on restraint system interaction, i.e., a combination of UN R137 and UN R21 to investigate interaction of restraint system with different body shapes. Define load case dependent requirements for Human Models, define also testable conditions. | EqOP IWG 7th session - Transport - Vehicle Regulations - UNECE Wiki
How to apply the Gender–Responsive Guidelines | Discussed | IWG | 7 | 2024-09-10 | Stockholm | Application of the Gender–Responsive Guidelines in the UN IWG EqOP work | EqOP IWG 7th session - Transport - Vehicle Regulations - UNECE Wiki
Brain injuries - assessment | Presented | TF5 | 2 | 2024-09-18 | On-line | Dr Matsui presented and mentioned that the rate of strain does affect outcome of diffuse axonal injury further to the strain itself. | 2nd meeting TF5 - Transport - Vehicle Regulations - UNECE Wiki
Brain injuries - assessment | Discussed | TF5 | 2 | 2024-09-18 | On-line | It was noted that we should not get lost in details, albeit important, a general understanding of mechanisms can suffice for assessments. | 2nd meeting TF5 - Transport - Vehicle Regulations - UNECE Wiki
Injuries to upper and lower extremities | Presented | TF5 | 2 | 2024-09-18 | On-line | Prof Forman presented statistics on both leg and arm injuries, which both have high prevalence for women. | 2nd meeting TF5 - Transport - Vehicle Regulations - UNECE Wiki
Pregnancy fatalities | Presented | TF5 | 2 | 2024-09-18 | On-line | Prof Forman introduced also a study of pregnancy fatalities, which have the same rate as fatalities to children in road crashes. | 2nd meeting TF5 - Transport - Vehicle Regulations - UNECE Wiki
Permanent medical impairment | Presented | TF5 | 3 | 2024-10-02 | On-line | Prof Kullgren presented distributions of injuries leading to permanent medical impairment (PMI) for different impact directions. | 3rd meeting TF5 - Transport - Vehicle Regulations - UNECE Wiki
Lower extremity injury | Presented | TF5 | 3 | 2024-10-02 | On-line | Dr Brumbelow presented a study on lower extremity injury types in frontal crashes on female belted drivers in modern vehicles. | 3rd meeting TF5 - Transport - Vehicle Regulations - UNECE Wiki
Lower extremity injury - assessment | Presented | TF5 | 3 | 2024-10-02 | On-line | The Female Lower Extremity Injury Criterion (FLEIC) was presented, a statistically derived criterion shown to predict LX injuries to females. | 3rd meeting TF5 - Transport - Vehicle Regulations - UNECE Wiki
Wrap up the workshop in Stockholm | Discussed | TF2 | 5 | 2024-11-04 | On-line | The idea of creating a semi-static load-taking will risk becoming more complicated than a mandatory dynamic test. | 5th meeting TF2 - Transport - Vehicle Regulations - UNECE Wiki
CLEPA R17 proposal | Agreed | TF2 | 5 | 2024-11-04 | On-line | CLEPA noted that the current backset test and other requirements will remain, and the CLEPA proposal will just improve the situation. | 5th meeting TF2 - Transport - Vehicle Regulations - UNECE Wiki
Status report from task forces | Agreed | IWG | 8 | 2024-11-07 | On-line | TF4 not yet started; potentially a TF4 meeting in early 2025 to create a workplan for TF4. | EqOP IWG 8th session - Transport - Vehicle Regulations - UNECE Wiki
Draft report to GRSP-76 from IWG | Agreed | IWG | 8 | 2024-11-07 | On-line | Agreed on the main points. Question if the use of HBM also should be taken in GRSP: noted this discussion in GRSP should be taken at a later point in time. | EqOP IWG 8th session - Transport - Vehicle Regulations - UNECE Wiki
Conclusions UN Gender-responsive guidelines | Discussed | IWG | 8 | 2024-11-07 | On-line | The chairs will prepare a first list where the gender-responsive guidelines should be applied, for the May 2025 session of GRSP. | EqOP IWG 8th session - Transport - Vehicle Regulations - UNECE Wiki
Soft tissue neck injuries in frontal and side | Presented | TF5 | 4 | 2024-11-20 | On-line | Prof Svensson concluded that women are at higher risk, with more prevalent symptoms like neck pain, headaches, and neurological issues. | 4th meeting of TF5 - Transport - Vehicle Regulations - UNECE Wiki
Brain injuries - field cases | Presented | TF5 | 4 | 2024-11-20 | On-line | Prof Kleiven reviewed several detailed reconstructions of traumatic brain and skull injuries using subject-specific models. | 4th meeting of TF5 - Transport - Vehicle Regulations - UNECE Wiki
Brain injuries - assessment | Presented | TF5 | 4 | 2024-11-20 | On-line | Prof Kleiven mentioned that the DAMAGE model is an appr of the GHBMC brain model, shows corr. between angular motion and brain strain. | 4th meeting of TF5 - Transport - Vehicle Regulations - UNECE Wiki
Next step of TF5 as of 20 Nov 2024 | Agreed | TF5 | 4 | 2024-11-20 | On-line | Brain and lower legs injuries kept on the TF5 agenda; neck injuries in rear-end impacts are for TF2; neck injuries in frontal are for TF4. | 4th meeting of TF5 - Transport - Vehicle Regulations - UNECE Wiki
Load case for proof of concept of VCT | Agreed | TF3 | 6 | 2024-11-22 | On-line | As decided in the IWG EqOP meeting on September 10: a combination of UN R137-sled and UN R21 is used as loadcase for the proof of concept. | 6th meeting/workshop TF3 - Transport - Vehicle Regulations - UNECE Wiki
PoC workplan with 3 different levels | Agreed | TF3 | 6 | 2024-11-22 | On-line | Work on 3 Levels: Level 3: HBM injury risk prediction; Level 2: HBM kinematics (existing in GTR9 proposals); Level 1: VCT with ATD as defined in regulatory texts. Level 2.5 could be in between level 3 and 2 to look at tendencies / robustness and not absolute values of the injury risk. Start working on 3 and use 2 and 1 as fallback. | 6th meeting/workshop TF3 - Transport - Vehicle Regulations - UNECE Wiki
Definition of Fail and Success in the PoC | Discussed | TF3 | 6 | 2024-11-22 | On-line | Definition of evaluation criteria to judge pass / fail: expected safety benefit large enough, trustworthy enough, simulation models good enough, feasibility within 10 years. | 6th meeting/workshop TF3 - Transport - Vehicle Regulations - UNECE Wiki
Report to GRSP-76 from IWG | Presented | GRSP | 76 | 2024-12-02 | Geneva | Main content: 1) Status of respective Task Force, 2) VCT and Proof of Concept, 3) Priorities, 4) Next steps. | IWG EqOP – 8th meeting
CLEPA R17 proposal | Agreed | GRSP | 76 | 2024-12-02 | Geneva | GRSP adopted informal document GRSP-76-47-Rev.1. | (WP.29/GRSP) Working Party on Passive Safety (76th session) ¦ UNECE
GRSP-76 Report | Agreed | GRSP | 76 | 2024-12-02 | Geneva | Priorities of the IWG EqOP agreed and decided: 1) Rear-end (soft tissue neck injuries); 2) Frontal (restraint systems); 3) Extension of assessments towards currently not considered injury types with high frequency and risk of permanent medical impediment (PMI) (brain, soft tissue neck and lower extremities) | ECE-TRANS-WP29-GRSP-76e.pdf
PoC load case, criteria and workplan | Agreed | CPs | 1 | 2024-12-02 | Geneva | Ad hoc meeting between Contracting Parties on Virtual Crash Testing, see notes (this meeting is logged as a follow-up of the Nov 22 TF3). | Ad hoc meetings TF3 - Transport - Vehicle Regulations - UNECE Wiki
PoC workplan: UN R137/R21 | Agreed | CPs | 1 | 2024-12-02 | Geneva | Simulations in vehicle sled environment to check robustness of restraint system. | Ad hoc meetings TF3 - Transport - Vehicle Regulations - UNECE Wiki
PoC workplan: UN R137/R21 | Agreed | CPs | 1 | 2024-12-02 | Geneva | Use validation procedure as “side-product” to clarify validation in UN R21. | Ad hoc meetings TF3 - Transport - Vehicle Regulations - UNECE Wiki
PoC workplan: UN R137/R21 | Agreed | CPs | 1 | 2024-12-02 | Geneva | Include testable conditions for the possibility to check if the simulations represent the real car and for CoP. | Ad hoc meetings TF3 - Transport - Vehicle Regulations - UNECE Wiki
PoC workplan: Time perspective | Agreed | CPs | 1 | 2024-12-02 | Geneva | Aim of PoC to address all questions until 2027 while having a long-term perspective (~10 years). | Ad hoc meetings TF3 - Transport - Vehicle Regulations - UNECE Wiki
Small series (if no simulation models of cars) | Agreed | CPs | 1 | 2024-12-02 | Geneva | Issue with small series where no simulation models exist should be solved on regional level such as for the other regulations. | Ad hoc meetings TF3 - Transport - Vehicle Regulations - UNECE Wiki
Evaluation Croteria for PoC | Agreed | CPs | 1 | 2024-12-02 | Geneva | Consensus on evaluation criteria to judge pass / fail: expected safety benefit large enough, trustworthy enough, simulation models good enough, feasibility within 10 years, can be implemented by industry and CPs | Ad hoc meetings TF3 - Transport - Vehicle Regulations - UNECE Wiki
IIHS’s rear impact seat parameter project | Presented | TF2 | 6 | 2025-01-23 | On-line | The project goals are to identify injury metrics of occupant response and seat safety performance, and correlate injury metrics. | 6th meeting TF2 - Transport - Vehicle Regulations - UNECE Wiki
Repeatability & Reproducibility of BioRID II | Presented | TF2 | 6 | 2025-01-23 | On-line | Recommendations for R&R of BioRID II are available. | 6th meeting TF2 - Transport - Vehicle Regulations - UNECE Wiki
Roadmap to physical EvaRID | Presented | TF2 | 6 | 2025-01-23 | On-line | Release date is not yet announced. | 6th meeting TF2 - Transport - Vehicle Regulations - UNECE Wiki
Dynamic test of seatback | Discussed | TF2 | 6 | 2025-01-23 | On-line | Different views regarding the justification of dynamic testing with human surrogate, for example BioRID. | 6th meeting TF2 - Transport - Vehicle Regulations - UNECE Wiki
Correct adjustment of headrests | Discussed | TF2 | 6 | 2025-01-23 | On-line | The Technical Expert of CLEPA highlighted that injury risk may be influenced by how users adjust headrests: Discussed and posted as an agenda item for next meeting. | 6th meeting TF2 - Transport - Vehicle Regulations - UNECE Wiki
Correct adjustment of headrests | Agreed | TF2 | 7 | 2025-03-20 | On-line | Agreement of the importance of correct headrest adjustment for whiplash protection. | 7th meeting TF2 - Transport - Vehicle Regulations - UNECE Wiki
Master Document | Presented | TF3 | 7 | 2025-03-25 | On-line | A living presentation (a “Master-Document” ) which includes all points of the procedure we have agreed upon was presented. | 7th meeting/workshop TF3 - Transport - Vehicle Regulations - UNECE Wiki
Master Document | Agreed | TF3 | 7 | 2025-03-25 | On-line | Agreement on the Master Document and that it will be useful. | VCT Master Document - Transport - Vehicle Regulations - UNECE Wiki
Informal draft mid-term report | Presented | IWG | 9 | 2025-04-03 | On-line | The chairs presented a draft mid-term report (Draft EqOP May_2025-04-03) summarizing discussions since the beginning of the EqOP, intended to make the prioritization of the IWG more transparent. Note that this draft report was only circulated to meeting participants. | EqOP IWG 9th session - Transport - Vehicle Regulations - UNECE Wiki
Purpose of PoC - overall goal | Agreed | TF3 | 8 | 2025-04-22 | On-line | Discussion again and agreement on the overall goal of achieving real-life benefits. | 8th meeting/workshop TF3 - Transport - Vehicle Regulations - UNECE Wiki
Robustness (varied human body conditions) | Discussed | TF3 | 8 | 2025-04-22 | On-line | We discussed again the goal of ensuring protection of different sizes and shapes of human bodies (robustness). Note that we have a clear task in the ToR to work towards regulations which address a diverse population | 8th meeting/workshop TF3 - Transport - Vehicle Regulations - UNECE Wiki
Single point tests | Discussed | TF3 | 8 | 2025-04-22 | On-line | We aim to address the potential shortcomings of optimization of crash performance for specific test conditions and test dummies in a narrow way which may be detrimental to the protection of a diverse population. | 8th meeting/workshop TF3 - Transport - Vehicle Regulations - UNECE Wiki
Informal draft mid-term report | Presented | IWG | 10 | 2025-04-24 | On-line | The chairs presented an updated draft mid-term report (Draft EqOP May_2025-04-23) summarizing discussions since the beginning of the EqOP, intended to make the prioritization of the IWG more transparent. Note that this draft report was only circulated to meeting participants. | EqOP IWG 10th session - Transport - Vehicle Regulations - UNECE Wiki
ESV Report on Equity Issues | Discussed | IWG | 10 | 2025-04-24 | On-line | The IWG discussed and concluded that there is still an opportunity to prepare a report for the upcoming ESV conference provided volunteers are available to contribute to this effort. | EqOP IWG 10th session - Transport - Vehicle Regulations - UNECE Wiki
Ad hoc meeting on May 07 in GRSP - way forward | Agreed | GRSP | 77 | 2025-05-05 | Geneva | We will revisit the accidentology regarding equity and we will define injury mechanisms as far as feasible. | IWG Ad hoc meeting 7 May 2025 - Transport - Vehicle Regulations - UNECE Wiki
Ad hoc meeting on May 07 in GRSP - way forward | Agreed | GRSP | 77 | 2025-05-05 | Geneva | Agreed claim for a workshop on equity issues in frontal impact and their causes. | IWG Ad hoc meeting 7 May 2025 - Transport - Vehicle Regulations - UNECE Wiki
Report to GRSP-77 from IWG | Presented | GRSP | 77 | 2025-05-05 | Geneva | The chairs presented an updated mid-term report summarizing discussions since the beginning of the EqOP and intended to make the prioritization of the IWG more transparent. | (Sweden) Report of EqOP ¦ UNECE
GRSP-77 Report | Agreed | GRSP | 77 | 2025-05-05 | Geneva | The experts from Sweden and Austria briefed GRSP on the recent activities and next steps of EqOP (informal document GRSP-77-29-Rev.1). | ECE-TRANS-WP29-GRSP-76e.pdf
Recap of the GRSP-77 discussions | Presented | IWG | 11 | 2025-06-02 | On-line | The chairs made a recap of the GRSP-77, including next steps based on the ad hoc meeting and as presented in GRSP-77. | EqOP IWG 11th session - Transport - Vehicle Regulations - UNECE Wiki
Workshop in September 2025 | Discussed | IWG | 11 | 2025-06-02 | On-line | The chairs introduced the workshop, a full IWG workshop but linked to the task force on restraint system requirements. The chairs solicited volunteers to participate in a planning committee. | EqOP IWG 11th session - Transport - Vehicle Regulations - UNECE Wiki
Reading List | Discussed | IWG | 11 | 2025-06-02 | On-line | A separate section on wiki, which we will call Accidentology will contain the Reading List. | EqOP IWG 11th session - Transport - Vehicle Regulations - UNECE Wiki
ISO scores ok, regarding virtual testing with ATDs | Discussed | TF3 | 9 | 2025-06-04 | On-line | Presentation on ISO scores from virtual testing at China NCAP by CATARC: promising results in vehicle environment and plans to include these load cases for monitoring in future protocol updates | 9th meeting/workshop TF3 - Transport - Vehicle Regulations - UNECE Wiki
Requirements on vehicle interior part models | Discussed | TF3 | 9 | 2025-06-04 | On-line | Presentation on Validation of Airbag Models by Autoliv: airbag models subject to German industry standard since years; need for same effort of all components which influence occupant protection | 9th meeting/workshop TF3 - Transport - Vehicle Regulations - UNECE Wiki
Validation and qualification of HIII models | Discussed | TF3 | 9 | 2025-06-04 | On-line | Presentation on Validation of HIII Simulation Models by Humanetics: on the CP510 qualification requirements for H3 models. Showed that their ATD simulation models meet all requirements. | 9th meeting/workshop TF3 - Transport - Vehicle Regulations - UNECE Wiki
Validation and qualification of HIII models | Discussed | TF3 | 9 | 2025-06-04 | On-line | Presentation on Validation of HIII Simulation Models by ACEA: Detailed explanation of the three-stage model qualification process including a review of remaining challenges. | 9th meeting/workshop TF3 - Transport - Vehicle Regulations - UNECE Wiki
Topics for upcoming meetings | Agreed | TF3 | 9 | 2025-06-04 | On-line | 1) Component-level validation for interior/restraint systems – which WG/forum? 2) HBM – status on validation, qualification, usability. 3) Traceability – what and how? | 9th meeting/workshop TF3 - Transport - Vehicle Regulations - UNECE Wiki
Additional next step, besides the topics | Agreed | TF3 | 9 | 2025-06-04 | On-line | Discuss how to proceed with the proof of concept – what’s needed and what’s already in place? | 9th meeting/workshop TF3 - Transport - Vehicle Regulations - UNECE Wiki
Workshop agenda update | Agreed | IWG | 12 | 2025-07-30 | On-line | The workshop agenda will be updated according to meeting discussion and decision. | EqOP IWG 12th session - Transport - Vehicle Regulations - UNECE Wiki
Workshop preparation material presented | Presented | IWG | 12 | 2025-07-30 | On-line | The workshop preparation material, which includes a summary of the abstracts of the Reading List and a preparation check list, will be attached to the workshop invitation. | EqOP IWG 12th session - Transport - Vehicle Regulations - UNECE Wiki
The IWG EqOP Progress Dashboard | Agreed | IWG | 12 | 2025-07-30 | On-line | The Decision List will get a new name: The IWG EqOP Progress Dashboard. | EqOP IWG 12th session - Transport - Vehicle Regulations - UNECE Wiki
The Progress Dashboard in the next IWG meeting | Agreed | IWG | 12 | 2025-07-30 | On-line | The IWG EqOP Progress Dashboard will be e-mailed attached to the meeting invitation of the next IWG meeting (October 15) and will be on the agenda of the next IWG meeting for approval. | EqOP IWG 12th session - Transport - Vehicle Regulations - UNECE Wiki
Recap and update of relevant issues | Presented | TF2 | 8 | 2025-09-03 | On-line | We had 3 presentations: 1) Head restraint geometry and seat interaction by Chalmers; 2) Update on parametric study of FE seats in rear impact by UVA/IIHS; 3) Relevant discussion topics by UTAC | 8th meeting TF2 - Transport - Vehicle Regulations - UNECE Wiki
Focus on the complete seating system | Agreed | TF2 | 8 | 2025-09-03 | On-line | We agreed to focus attention on the complete seating system—evaluating the combined performance of the seatback and headrest—either by complementing static testing | 8th meeting TF2 - Transport - Vehicle Regulations - UNECE Wiki
Occupant safety in frontal impacts | Presented | Workshop | 4 | 2025-09-23 | Graz | Extensive discussions and presentations focused on improving frontal impact safety and addressing equity issues for diverse occupants | Equity issues in frontal impacts relevant for restraint systems - In-person workshop - Transport - Vehicle Regulations - UNECE Wiki
Equity issues in frontal impacts | Discussed | Workshop | 4 | 2025-09-23 | Graz | Females and elderly occupants face higher injury risks for several injury types in certain crash scenarios | Equity issues in frontal impacts relevant for restraint systems - In-person workshop - Transport - Vehicle Regulations - UNECE Wiki
Summary doc #1 - consensus on equity issues | Agreed | Workshop | 4 | 2025-09-23 | Graz | Equity issues in vehicle safety based on frontal impact field data - disparities | Equity issues in frontal impacts relevant for restraint systems - In-person workshop - Transport - Vehicle Regulations - UNECE Wiki
Summary doc #2 - consensus on hypotheses | Agreed | Workshop | 4 | 2025-09-23 | Graz | Disparities depend on complex interactions involving occupant physiology and the fit of seatbelts, seats and airbags, which are affected by body shape and seat positioning | Equity issues in frontal impacts relevant for restraint systems - In-person workshop - Transport - Vehicle Regulations - UNECE Wiki
Summary document, complete | Agreed | IWG | 13 | 2025-10-15 | On-line | Approval and plan to submit a summary of agreed equity issues and injury causation hypotheses (the summary document of the workshop in Graz) to GRSP 78 | EqOP IWG 13th session - Transport - Vehicle Regulations - UNECE Wiki
Task force to improve frontal test procedures | Agreed | IWG | 13 | 2025-10-15 | On-line | The IWG decided to form and initiate a new Task Force focused on frontal impacts and restraint system requirements (TF4) | EqOP IWG 13th session - Transport - Vehicle Regulations - UNECE Wiki
IWG EqOP Dashboard | Agreed | IWG | 13 | 2025-10-15 | On-line | Approval and posting of the IWG EqOP Progress Dashboard | EqOP IWG 13th session - Transport - Vehicle Regulations - UNECE Wiki
HBM qualification methodology | Presented | TF3 | 10 | 2025-10-16 | On-line | Presentation by TUG: HBM qualification methodology to ensure biofidelity and comparability in virtual testing | 10th meeting/workshop TF3 - Transport - Vehicle Regulations - UNECE Wiki
Model traceability procedures | Presented | TF3 | 10 | 2025-10-16 | On-line | Presentation by IIHS: Model traceability procedures for securing simulation integrity and building confidence in virtual testing frameworks, especially concerning intellectual property | 10th meeting/workshop TF3 - Transport - Vehicle Regulations - UNECE Wiki
Proof of Concept (PoC) workplan | Agreed | TF3 | 10 | 2025-10-16 | On-line | The Master Document was updated in the meeting; note that it is posted on separate page of the UN Wiki (on VCT Master Document under TF3 - link also provided in the minutes) | 10th meeting/workshop TF3 - Transport - Vehicle Regulations - UNECE Wiki
Proof of Concept (PoC) workplan | Agreed | TF3 | 10 | 2025-10-16 | On-line | Keep the PoC workplan as is and keep it in a ppt format until further notice | 10th meeting/workshop TF3 - Transport - Vehicle Regulations - UNECE Wiki
Next steps | Agreed | TF3 | 10 | 2025-10-16 | On-line | Determine 1) value (benefit) of HBM to close equity issues, 2) if it possible to use HBMs in regulations within the next 10 years, 3) readiness of respective component models | 10th meeting/workshop TF3 - Transport - Vehicle Regulations - UNECE Wiki
Top priorities (topics) frontal impact | Presented | TF4 | 1 | 2025-11-06 | On-line | Chair presented: improving test procedures considering a wider range of crash speeds, e.g., lower speeds, occupant sizes/shapes, and seat adjustments to ensure robustness | 1st meeting TF4 - Transport - Vehicle Regulations - UNECE Wiki
Robustness while avoiding an increase in tests | Discussed | TF4 | 1 | 2025-11-06 | On-line | We highlighted the tension between increasing the robustness of restraint systems on various crash scenarios and avoiding an undue increase in the number of official type-approval crash tests | 1st meeting TF4 - Transport - Vehicle Regulations - UNECE Wiki
Technical documentation vs. more crash testing | Discussed | TF4 | 1 | 2025-11-06 | On-line | Discussion on priorities; suggestions ranging from addressing seatbelt misuse and abdominal injuries to using technical documentation instead of more crash testing to ensure system robustness | 1st meeting TF4 - Transport - Vehicle Regulations - UNECE Wiki
Prioritize the agreed topics until next meeting | Agreed | TF4 | 1 | 2025-11-06 | On-line | Further analysis of rear-row and abdominal injury accident data, as well as collecting ideas for robustness evaluation, and having participating organizations prioritize the agreed-upon topics | 1st meeting TF4 - Transport - Vehicle Regulations - UNECE Wiki
Seat Evaluation Tools (SETs) | Presented | TF2 | 9 | 2025-11-06 | On-line | Presentation by VTI: risk for PMI derived from Folksam injury data, for males and females, are compared with the NIC results obtained using the SET 50F and 50M models in the test seats | 9th meeting TF2 - Transport - Vehicle Regulations - UNECE Wiki
Seat Evaluation Tools (SETs) | Discussed | TF2 | 9 | 2025-11-06 | On-line | Key discussions revolved around the Swedish expert's presentation on a research project using Seat Evaluation Tools (SETs) | 9th meeting TF2 - Transport - Vehicle Regulations - UNECE Wiki
Recap of previous discussions | Presented | TF2 | 9 | 2025-11-06 | On-line | Chair presented: recap and conclusions from previous discussions, while outlining topics for a future workshop focused on research gaps and dynamic testing | 9th meeting TF2 - Transport - Vehicle Regulations - UNECE Wiki
Dynamic testing to evaluate neck injury protection | Discussed | TF2 | 9 | 2025-11-06 | On-line | We discussed static tests versus dynamic testing to evaluate neck injury protection, with a general consensus that dynamic methods will be necessary to ensure equitable protection | 9th meeting TF2 - Transport - Vehicle Regulations - UNECE Wiki
Workshop in 2026 | Agreed | TF2 | 9 | 2025-11-06 | On-line | Agreed to further exploring the feasibility of mandatory dynamic testing during a dedicated workshop in 2026 | 9th meeting TF2 - Transport - Vehicle Regulations - UNECE Wiki