## Slide 1
Date | Meeting | Detail
March 2023 24 27 March | 1st Informal meeting Web | Confirmation of TOR, Input from CP (e.g. NCAP) and industry(e.g. State of the art), Traffic accident data, etc.
Early or Middle of May 2023 15 16 17 of May | 2nd Informal meeting Web | Skelton document, Discussion about requirements
May 22-26 2023 | 16th GRVA | Report of IWG activities
19, 20, 21 September 2023 | 3th Informal meeting Germany (In-person) | Discussion about requirements and test procedures
September 25-29 2023 | 17th GRVA | Report of IWG activities
21, 22, 24 November 2023 | 4th Informal meeting Japan (In-person) | Discussion about requirements and test procedures
ACPE-03-13
Draft schedule of ACPE informal meeting

## Slide 2
Date | Meeting | Detail
17-18 January 2024 | 5th Informal meeting Web (3 hours: 8-11CET) | Discussion about requirements and test procedures
22-26 January 2024 | 18th GRVA | Report of IWG activities Regulation will submit as informal document
27-29 February 2024 | 6th Informal meeting In-Person (London) | Discussion about requirements and test procedures Second step approach
26 March 2024 (8 – 11 CET) | 7th Informal meeting in Web | Maintenance of 00 series proposal (15th March is deadline of comment to 7th IWG)
20-24 May 2024 | 19th GRVA | Report of IWG activities Regulation will submit as 00 series of formal document
About activity of informal meeting
Method:
Meeting will be held by in-person or Teams.
Days and hours:
3 days 6 hours with in-person
3 days 3 hours with Teams

## Slide 3
Date | Meeting | Detail
17-21 June 2024 (3 days) | 8th Informal meeting in Asia | Discussion about requirements and test procedures for 01 series
[18-20 September] 2024 | 9th Informal meeting in Germany | Discussion about requirements and test procedures for 01 series
23-27 September 2024 | 20th GRVA | Report of IWG activities Regulation will submit as informal document
[21-25] October 2024 | 10th Informal meeting in Web | Discussion about requirements and test procedures for 01 series Deadline for submission of formal document to 21th GRVA
January 2025 (Before GRVA) | 11th Informal meeting in In-person or Web | Discussion about requirements and test procedures for 01 series
January 2025 | 21th GRVA | Report of IWG activities Regulation will submit as 01 series of formal document
IWG will propose the extension of our activities until January 2025.