## Slide 1: Session orientation and status of work
Document ADS-05-04
5th ADS IWG session
9-13 December 2024

## Slide 2: Session Agenda

## Slide 3: Draft general calendar
 | 2024 |  |  |  |  |  |  |  |  |  |  |  | 2025 |  |  |  |  |  |  |  |  |  |  |  | 2026 |  |  |  |  |  |  |  |  |  |  | 
 | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D
WP.29 sessions |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
GRVA sessions |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
ADS IWG sessions |  |  |  | 1 | 2 |  | 3 |  |  | 4 |  | 5 |  | 6 |  | 7 |  |  | 8 |  | 9 | 10 |  |  |  |  |  |  |  |  |  |  |  |  |  | 
GRVA Workshops (partial) |  |  |  |  |  | 1 |  |  | 2 | 3 |  | 4 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Initial “common” provisions |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Initial draft GTR and UNR |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Informal draft GTR and UNR |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Formal GTR and UNR to GRVA |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
GRVA approval of GTR and UNR |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
WP.29 adoption of GTR and UNR |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 4: Draft general work plan
December 2024: Common provisions and gap identification complete
  Transposition of guidelines and understanding of remaining workload
February 2025: GTR/UNR parallel development launch
  Work plan and initial tasking for finalising GTR and UNR submissions
April 2025: Initial draft GTR and UNR (input from WS)
  Consolidation of proposed contents into draft GTR and UNR
July 2025: Second reading draft GTR and UNR
  Consolidation of further contents to complete drafts
September 2025: Informal GTR/UNR submissions to GRVA
  Remainder resolution and informal drafts for September GRVA session
November 2025: Formal GTR/UNR submissions to GRVA
  Finalisation of working documents for submission to January 2025 GRVA session

## Slide 5: Areas of work
Phase 1: Requirements
Scope, Purpose, Definitions
Safety Management System
DDT performance
User safety requirements
Safety Assessment
  Safety concept
  Safety case
Virtual Testing Credibility Assessment
In-Service Monitoring and Reporting
Reference regulations/standards
Phase 2: Assessment/Test Methods
SMS Audit
Safety Assessment
Virtual, Track, Real-World Testing
In-Service Monitoring and Reporting

## Slide 6: 5th session objectives
End of Phases 1 and 2
  Transposition of guidelines into common regulatory provisions
  Identify gaps that need to be filled in submissions to GRVA next November
Enable transition to Phase 3 (GTR/UNR drafting)
  Consensus on common provisions where possible
  Identification of open issues where consensus not achieved
  Guidance on structural/procedural directions
Chairs will use outcomes of this session as the basis for initial drafting of GTR and UNR documents. Initial drafts will transpose common provisions into each structure with placeholders for gaps/open issues. Chairs will use this exercise to propose priorities and work plan for completing GTR and UNR submissions by the first week of November.

## Slide 7: Four blocks
Safety Management System
Requires the manufacturer to document its processes for managing and mitigating risk throughout the ADS lifecycle.
Safety Concept
Requires the manufacturer to describe the ADS via documentation on the outcomes from applying the SMS to the ADS design and development.
Safety Case
Requires the manufacturer to document the outcomes of its verification and validation of the ADS safety concept via a structured, evidence-based argument.
Safety Management System Audit
Requires a review and validation of the manufacturer’s SMS for compliance with the specifications of the regulation (GTR or UNR).
Safety Assessment
Requires a review and preliminary validation of the manufacturer’s safety case for the ADS as compliant with the specifications of the regulation.
ADS Virtual Testing
Requires selective verification and validation of evidence in the safety case that was generated via the manufacturer’s virtual testing toolchain.
ADS Track Testing
Requires selective verification and validation of the evidence in the safety case generated via track tests, including confirmation of virtual testing results.
Real-World Test Drives
Requires verification and validation of the safety-case argumentation via engineered testing on public roads under uncontrolled conditions.
In-Service Monitoring/Reporting
Requires the manufacturer to monitor ADS performance, report anomalies and data, and remedy issues. Also enables targeted information sharing.

## Slide 8: “Alignment” perspective
Safety Management System
Requires the manufacturer to document its processes for managing and mitigating risk throughout the ADS lifecycle.
Safety Concept
Requires the manufacturer to describe the ADS via documentation on the outcomes from applying the SMS to the ADS design and development.
Safety Case
Requires the manufacturer to document the outcomes of its verification and validation of the ADS safety concept via a structured, evidence-based argument.
Safety Management System Audit
Requires a review and validation of the manufacturer’s SMS for compliance with the specifications of the regulation (GTR or UNR).
Safety Assessment
Requires a review and preliminary validation of the manufacturer’s safety case for the ADS as compliant with the specifications of the regulation.
ADS Virtual Testing
Requires selective verification and validation of evidence in the safety case that was generated via the manufacturer’s virtual testing toolchain.
ADS Track Testing
Requires selective verification and validation of the evidence in the safety case generated via track tests, including confirmation of virtual testing results.
Real-World Test Drives
Requires verification and validation of the safety-case argumentation via engineered testing on public roads under uncontrolled conditions.
In-Service Monitoring/Reporting
Requires the manufacturer to monitor ADS performance, report anomalies and data, and remedy issues. Also enables targeted information sharing.