## Slide 1
Status
of
report
the
3rd
GRVA
Workshops
ADS
November 2024
Document ADS-05-28-Rev.1
5th ADS-IWG session
9-13 December 2024
Submitted by the IWG Ambassadors to the GRVA ADS Workshops

## Slide 2
Content
•
Organizational aspects
Structure of work
Status update since October
Items for discussion
Future sessions
•
•
•
•

## Slide 3
Organization aspects
•
•
Leadership: Richard Damm, Chen Chunmei, Takashi Naono
Ambassadors: Linda Rasmussen (Australia), Peter Striekwold (NL)
•
Three tasks:
1. Development of administrative requirements for GTR ADS
2. Development of administrative requirements for UNR ADS
3. Development of an interpretation document
•
Planning:
first draft for task 1 & 2 available in January 2025
final version for task 1 & 2 available in May 2025

## Slide 4
Structure and OPI’s
for
GTR
ADS
(SAE International)
Support by Roy, Jean- Michael (CA)
Detailed Task Decomposition Framework Structure and OPIs Table for GTR. (This file is expecting small changes as informed by Jiajie Wu in last OPI Meeting)
Task
Topic
Description/comments
OPI
1
Statement of technical rationale
The task is to prepare a statement of technical rationale that can be included in a preamble to both the GTR and
UNR. This section is specifically composed of the following parts, it should be summarized and concluded
after the following main parts are completed.
Wu, Jiajie (CN), Support by Russ Shields (ITU)
/
Appendix:Development of GTR
The task is to prepare a document setting out how the GTR was developed covering these key headings
/
2
Introduction
The task is to provide an overview and clear and concise summary of the GTR. It should outline the objectives of the regulation, the reasons for its development, and the agreements made by CPs to develop such a GTR.
Zhang, Jiarui(CN)
3
Procedural background
The task is to list details of the procedural steps and historical context that led to the development of the GTR. It includes information on the meetings, discussions, and decisions that were part of the regulatory process.
Roy, Jean- Michael (CA)
4
Technical background
The task is to provide a comprehensive overview of the technical aspects relevant to the GTR. It includes detailed information on the technologies, systems, and engineering principles that underpin the regulation.
Zhou, Bolin (CN) Support by Dan Smith
5
Principle for developing the regulation
The task is to outline the fundamental principles and guiding philosophies behind the development of the GTR.
Roy, Jean- Michael (CA)
6
Technical rationale and justification
The task is to provide a detailed justification for the technical requirementsspecified in the GTR. It includes the rationale behind the technical standards, backed by data, research, analysis, etc.
Liu, Nan (CN)
/
Recommendations
/ (ADS IWG’s Task)
/
/
Existing regulations, directives, and international
voluntary standards
/ (ADS IWG’s Task)
/
7
Benefits and costs
The task is to prepare a Benefit/Cost analysis that can support contracting parties to implement the GTR and
UNR in their national legislation. It may include an analysis of the positive and negative impacts on safety,
environment, and industry, as well as the economic implications for manufacturers, consumers, and regulatory
bodies accordingly.
Wu, Jiajie (CN), Claus Pastor (GERMANY), Support by Russ Shields (ITU)

## Slide 5
take up this section as
Structure
and
OPI’s
for
UNR
ADS
H. Matsukawa (JP)
H. Matsukawa (JP)
H. Matsukawa (JP)
H. Matsukawa (JP)
H. Matsukawa (JP)
(NL)
Detailed Task Decomposition and OPIs table for the UN Reg. on ADS
Para.
Topic
Description/comments
OPI
0
Introduction/preamble
Tbc.
May be derived mutatis mutandis from the introduction prepared for the UN GTR
*Cristina Galassi
(EC)was requested to
well in last OPI meeting
1
Scope
(Provided by the IWG on ADS)
/
2
Definitions
(Provided by the IWG on ADS)
/
3
Application for approval
The task is to draft the application for approval section of the UN R, including references to application forms and information documents as set out in annexes
Ramon Gouweleeuw
(NL)
4
Approval
The task is to draft the approval section of the UN R – this sets out the grounds on which a type approval authority will be satisfied and must issue an approval
Matt Claydon (UK)
5
Requirement
(Provided by the IWG on ADS)
/
6
Test
(Provided by the IWG on ADS)
/
7
Modification and extension of TA
The task is to draft the modification of vehicle type and extension of approval section of UN R – will require research to determine aspects of vehicle type that may affect compliance
Cristina Galassi (EC) +
8
Conformity of Production
The task is to draft the conformity of production section of the UN R
Cristina Galassi (EC) +
9
Penalties for non-conformity of
production
The task is to draft the penalties for
non-conformity of production
section of the UN R – should be
based on standard wording
Cristina Galassi (EC) +
10
Production definitively discontinued
The task is to draft the production
definitely discontinued section of
the UN R
Cristina Galassi (EC) +
11
Names and addressesof the Technical Services responsible for conducting approval tests and
of the Type Approval Authorities
The task is to draft the names and
addressesof technical services
section of the UN R – should be
based on standard wording
Cristina Galassi (EC) +
A1
Communication & Information
Document
The task is to draft the
communication and information
annex of the UN R
Ramon Gouweleeuw
A2
Arrangement of Approval Marks
The task is to draft the
Arrangement of approval marks annex of the UN R
Matt Claydon (UK)

## Slide 6
Previous Workshop sessions
•
1st Workshop (Online): held 5 June 2024 - Link
• Organizational matters clarified
2nd Workshop (Online): held 10-11 September 2024 - Link
•
•
•
•
Review of some initial input
Call for additional volunteers
Review of the OICA presentation on the “ADS Regulatory Approach”

## Slide 7
Outcome 3rd Workshop
(Hybrid, Beijing)
15+16
October
Documents:
UN GTR:
Link
- draft prepared by China
Germany, ITU, SAE.
together with experts from Canada,
- draft presented and discussed.
- suggestions for next version with regard to cost/benefit, inclusion of
Approval in the description and text on AI.
Type

## Slide 8
Outcome 3rd Workshop 15+16
(Hybrid, Beijing)
UNR:
October
-
-
draft prepared by Japan, UK and the Netherlands.
draft presented and discussed.
- proposed text for scope will be discussed with IWG ADS.
separate proposal from UK underlined the potential risks of both
requirements (different interpretations, mutual recognition) and
national/regional legislation (e.g. traffic rules)
-
generic
-
updated OICA proposal for adding feature approval on top of vehicle
approval.
- request to OICA to involve other participants in this proposal and see if this could
become an interpretation (Task 3)

## Slide 9
Special thanks!
•
The participants in Beijing had some great opportunities driving in
different driverless vehicles in normal traffic. All rides went very
smooth.
In addition, a symposium on automated driving systems was organized. Many participants from industry, authorities and science were present. Interesting presentations and demonstrations
•

## Slide 10
Items for discussion in IWG ADS
• Request to OPIs from both groups (IWG and WS) to start reading the draft documents from the other group

## Slide 11
Future
sessions
WS
Docum
(locati
Legend –
UN – UN office, Geneva
EC – European Commission, Brussels
CN – China
UK – United Kingdom
JP – Japan
RoK – Republic of Korea
TH – Thailand
Web – Online Meeting
Web-only sessions
Hybrid Session
In-Person event only
2024
2025
Jul
Aug
Sep
Oct
Nov
Dec
Jan
Feb
Mar
Apr
May
Jun
Jul
Aug
Sep
Oct
Nov
Dec
WP.29
sessions
12-15
UN
4-7
UN
24-27
UN
18-21
UN
GRVA
sessions
23-27
UN
20-24
UN
19-22
TH
2-6
TH
22-26
UN
Deliverables
ADS IWG Draft Docum ent of conten t
ADS + WS Inform al Docum ent
ADS +
Formal
ent
ADS IWG
sessions
9-12
EC
8-11
UK
9-13
RoK
17-19
Web
14-18
JP
19-21
Web
7-11
FIN
Early Sept. Web
6-10
CND
xx
Web
8-12
ASIA
on
TBC)
WS Draft Docum ent of conten t
GRVA ADS Workshops
10-11
Web
15-16
CN
17+19
Web
13-14
Web
25-26
Web
9-10
Web
18-19
GVA
4-5
Web