## Slide 1: WS Status update to IWG
19-05-2025
Document ADS-09-31
9th ADS IWG session
19 May 2025
Submitted by the ADS IWG Ambassadors to the GRVA ADS Workshops

## Slide 2: Agenda
Open issues WS
Task 3: interpretation document
Alignment of GTR and UNR administrative parts
Mid-term review
Upcoming WS meetings

## Slide 3: Open issues WS
GTR: almost done
UNR: two remaining discussions (expected to be solved in June)
Mutual recognition
R157 in relation to UNR ADS

## Slide 4: Task 3: Interpretation document
In the previous IWG we have explained the approach for Task 3 of the Workshop (Interpretations)
A draft list of priorities has been extracted from the IWG and WS meetings
The activity is expected to start after July 2025, and may continue even after June 2026

## Slide 5: Alignment GTR & UNR
We don’t expect changes in the draft GTR based on the content of the draft UNR
The main proposed change in the draft UNR is adding an introduction like we have in the draft GTR (corrected for a UNR where necessary). A proposal will be brought to the WS early June. Some minor changes in this introduction might also be included in the draft GTR introduction
Next step is alignment of the WS documents with the IWG documents (together with John Creamer)

## Slide 6: Mid-term review
Objective: review the content and process of our work so far
Planning: originally scheduled for early 2025, postponed till May in order to include as much progress as possible
Due to a technical issue it was not possible to send out the survey to all IWG and WS participants last week. This has now been resolved and will be sent this week. Questions can be found on the next slide
Responses are requested before 9 June. This allows evaluation of the inputs and preparation of the presentation of the results to the IWG in July, Helsinki

## Slide 7: Mid-term review questions
Do you expect that the current processes will allow adoption of the first GTR and UNR on ADS in the WP.29 June 2026 session?
If you expect that the current processes will not allow adoption of the first GTR and UNR on ADS in the WP. 29 June 2026 session, what should be done to speed it up?
Do you consider the GTR to be sufficiently mature for effective and efficient application?
  If not, what should be done about it?
Do you consider the UNR to be sufficiently mature for effective and efficient application?
  If not, what should be done about it?

## Slide 8: Upcoming WS meetings
10+11 June (Web)
18+19 September (in-person, Geneva)
4+5 November (Web)