## Foglio1
SLR-08-06
Task | Who | Deadline
Listing pending proposals* (start with SLR-01-06 Annex E) This will go to GRE-75 as informal document | Derwin + Karl (cross-check with Konstantin) | ASAP before next SLR (29 Feb 2016)
Present roadmap to AC.2 for initial feedback and advice | Michel | 7 March 2016 (120th WP.29/AC.2 session)
Submit roadmap (based on slide amended by Marcin) and skeleton of the new Regulations to GRE-75 (based on SLR-08-02) | Davide | Before GRE-75
Prepare finalised proposals (as supplements) for GRE-76. For doing so consolidated version of each Regulation to be simplified shall be prepared for SLR internal use only No merging of proposals amending the same Regs will be done | To be decided after GRE-75 | Deadline for GRE-76 (July 2016)
Prepare consolidated versions of each Regulation to be simplified These will become new revisions of the existing UN Regs | GRE Secretariat | Spring 2017
Drafting new provisions for DETA (latest status of discussion) | Geoff + Marking experts (taskforce within SLR) | GRE-76 (progress report) GRE-77 (proposal)
Bring back to R-48 the definitions (see SLR-07-04). Check the final wording | Karl + volunteers
Preparation of new simplified Regulations (first draft) | Karl | 9th SLR meeting (29 Feb 2016)
Development of 3 new UN Regulations - Road illumination devices - Signalling devices - Retro-reflecting devices | Taskforces within SLR: Volunteers to be defined at the next (9th) SLR meeting | GRE-76 (first informal proposals) GRE-77 (Rev. informal proposals) GRE-78 (official proposals)
*Pending proposals...
Proposals agreed by GRE but not submitted to WP.29 awaiting the outcome of the SLR
Proposals presented at GRE but not yet agreed
Proposals agreed by GRE but rejected by WP.29 => Additional changes never discussed by WP.29