## Slide 1
Schedule until summer holiday (it means you are not able to take vacation until you get job done)
Deadline for submission of working document to GRPE(93): 22nd July 2025
A-LCA 23rd session: 27th May 2025 >web
A-LCA 24th session: 24th – 25th June 2025 >Hybrid(physical venue is tbc)
April | May | June | July
GRPE |  |  | ★ Deadline(22nd)
Drafting Meeting ★ (24) 3rd deadline (14) | ★ 4th deadline (12) | ★ 5th deadline (tbd) | ★ Final deadline (tbd) including all IWG member
IWG | ★ #23 session* (27) | ★ #24 session** (24-25) | 
SG |  |  | 
**Final review
* pursue the agreement
on contradictory items
Develop methodology & text
feedbacks
feedbacks
feedbacks
Final
final refine
close to Final

## Slide 2: Updated Timeline
Each SGs provides their table of content
Official KOM
SG provides 3rd drafting : due date Friday 13th December
SG7 checks consistency, provides feedback and start writing
Milestones for SGs
13th of December : SGs leader provide draft
18th or 19th or 20th of December : SG7 meeting to provide feedbacks