# IWG PTI – Draft Action Plan

Reference document: ECE/TRANS/WP.29/2024/159

The aim of this document is to trigger the discussions within the group in order to define its next activities.

## Whole-life compliance (Nov 2024 – Nov 2027)

The discussions will take into account the document ECE/TRANS/WP.29/2023/89 and, where appropriate, consider its evolution.

## Measures to detect tampering: methods and supervision (June 2025 – Dec 2026)

General overview on tapering. Group members will be invited to submit their proposals, including a commitment to a time line.

Tampering on emissions systems: PN gasoline and NOx. In coordination with the Anti-tampering Task Force.

Odometer tampering: in coordination with the Task Force R39

## Advanced Driver Assistance Systems (ADAS) and Automated Driving Systems (ADS) (April 2025 – April 2027)

Proposal from Japan, necessary provisions for each UNR related the application of ePTI.

Analysis of possible options. Group members will be invited to submit their proposals, including a commitment to a time line.

## Consistency between the provisions of the 1968 Vienna Convention and the technical provisions for vehicles against the rules in the framework of the 1997 Vienna Agreement

Identification of subjects: Group members will be invited to submit their proposals, including a commitment to a time line.

## Guidance for PTI (Sept 2025 – April 2026)

Ongoing activity. To take into account the update of the EU’s Roadworthiness Package.

Development of a proposal to check the software version and integrity information. Group members will be invited to submit their proposals, including a commitment to a time line.

## Guidance for Roadside technical inspection and enforcement (Jan 2026 – Dec 2026)

To take into account the update of the EU’s Roadworthiness Package. Group members will be invited to submit their proposals, including a commitment to a time line.

## Gantt view:

| Working items | Task Lead | 2025 |  | 2026 |  | 2027 |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 1H | 2H | 1H | 2H | 1H | 2H |
| Whole-life compliance | Russian Federation |  | Vision/Structure/Concept | UN Regulations draft amendments | Approval WP29/GRs | Approval WP29/GRs | AC.1 |
| Provisions for testing ADAS/ADS at Periodic Technical Inspection | Russian Federation + FSD |  | Vision/Structure/Concept | Draft regulatory text | Approval WP29/GRs | Approval WP29/GRs |  |
| Specific information needed for testing electronic controlled safety and environmental relevant vehicle systems. | FSD |  |  | Vision/Structure/Concept | Draft regulatory text | Approval WP29/GRs |  |
| ePTI Provisions | JAPAN + FSD + KOTSA | Request to the WP.29 | Vision/Structure/Concept | UN Regulations draft amendments | Approval WP29/GRs | Approval WP29/GRs | AC.1 |
| The strategic vision of Periodical Technical Inspections of driverless vehicles. | CITA + Russian Federation |  | Vision/Structure/Concept |  | Draft regulatory text | Approval WP29/GRs | Approval WP29/GRs |
| Measures to detect tampering - PN measurement for gasoline vehicles | UN Taskforce Anti-tampering |  |  | Draft regulatory text | Approval WP29/GRs | Approval WP29/GRs | AC.4 |
| Draft amendment Rule 1 | CITA |  | Draft regulatory text | Approval WP29/GRs | Approval WP29/GRs |  | AC.4 |
| Draft amendment Rule 4 | CITA |  |  | Draft regulatory text | Approval WP29/GRs | Approval WP29/GRs | AC.4 |
| Draft amendment RE6 | CITA |  | Draft regulatory text | Approval WP29/GRs | Approval WP29/GRs |  |  |