## Sheet1
GR | Status | Expected date for GR-level working document | Notes
GRBP |  |  |  | GRBP February 2025 | GRBP September 2025 | WP.29 November 2025 | GRBP February 2026 | WP.29 March 2026 | WP.29 June 2026 | WP.29 November 2026
28 | Working document | 2025-09-01 | P1 |  | Working document |  |  |  | Working document
138 | Working document | 2025-09-01 | P1 |  | Working document |  |  |  | Working document
51 | Informal document | 2025-09-01 | P2 | Informal document | Working document |  |  |  | Working document
64 | TF-level draft |  |  |  | Informal document |  | Working document |  | Working document
141 | Informal document |  |  |  | Working document |  |  |  | Working document
142 | TF-level draft |  |  |  | Informal document |  | Working document |  | Working document
165 | Informal document |  |  |  | Working document |  |  |  | Working document
GRE |  |  |  | GRE April 2025 | GRE October 2025 | WP.29 November 2025 | WP.29 March 2026 | GRE April 2026 | WP.29 June 2026 | WP.29 November 2026
48 | Working document | 2025-10-01 | P1 | Informal document | Working document |  |  |  | Working document
45 | Informal document | 2025-10-01 | P2 |  | Working document |  |  |  | Working document
148 | Informal document | 2025-10-01 |  |  | Working document |  |  |  | Working document
GRPE |  |  |  | GRPE March 2025 | GRPE October 2025 | WP.29 November 2025 | GRPE March 2026 | WP.29 March 2026 | WP.29 June 2026 | WP.29 November 2026
83 | Informal document | 2025-10-01 | P1 | Informal document | Working document |  |  |  | Working document
154 | TF-level draft (in preparation) | 2025-10-01 | P1 |  | Informal document |  | Working document |  |  | Working document
24 | Informal document | 2025-10-01 |  |  | Informal document |  | Working document |  |  | Working document
68 | Informal document | 2025-10-01 |  |  | Informal document |  | Working document |  |  | Working document
49 | TF-level draft |  |  |  | Informal document |  | Working document |  |  | Working document
115 | TF-level draft |  |  |  | Informal document |  | Working document |  |  | Working document
143 | TF-level draft |  |  |  | Informal document |  | Working document |  |  | Working document
168 | Informal document | 2025-10-01 | P1 |  | Informal document |  | Working document |  |  | Working document
GRSG |  |  |  | GRSG April 2025 | GRSG October 2025 | WP.29 November 2025 | WP.29 March 2026 | GRSG April 2025 | WP.29 June 2026 | WP.29 November 2026
18 | TF-level draft (in preparation) |  | P1 |  | Working document |  |  |  | Working document
34 | TF-level draft (in preparation) |  |  |  | Working document |  |  |  | Working document
35 | Informal document | 2025-10-01 |  | Informal document | Working document |  |  |  | Working document
39 | Informal document | 2025-10-01 |  | Informal document | Working document |  |  |  | Working document
43 | Informal document | 2025-10-01 | P1 | Informal document | Working document |  |  |  | Working document
46 | Informal document | 2025-10-01 | P1 | Informal document | Working document |  |  |  | Working document
55 | TF-level draft (in preparation)
58 | TF-level draft (in preparation)
73 | TF-level draft (in preparation)
93 | TF-level draft (in preparation) |  |  |  | Working document |  |  |  | Working document
97 | TF-level draft (in preparation) |  |  |  | Working document |  |  |  | Working document
102 | TF-level draft (in preparation)
105 | TF-level draft (in preparation) |  |  |  | Working document |  |  |  | Working document
107 | Informal document | 2025-10-01 | P1 | Informal document | Working document |  |  |  | Working document
116 | Informal document | 2025-10-01 | P1 | Informal document | Working document |  |  |  | Working document
121 | Informal document | 2025-10-01 | P1 | Informal document | Working document |  |  |  | Working document
122 | Informal document | 2025-10-01 | P1 | Informal document | Working document |  |  |  | Working document
125 | Informal document | 2025-10-01 | P1 | Informal document | Working document |  |  |  | Working document
144 | Informal document | 2025-10-01 |  | Informal document | Working document |  |  |  | Working document
161 | Informal document | 2025-10-01 |  | Informal document | Working document |  |  |  | Working document
162 | Informal document | 2025-10-01 |  | Informal document | Working document |  |  |  | Working document
163 | Informal document | 2025-10-01 |  | Informal document | Working document |  |  |  | Working document
176 | TF-level draft (in preparation) |  |  |  | Working document |  |  |  | Working document
160 |  |  | EDR group! |  | Working document? |  |  |  | Working document?
169 |  |  | EDR group! |  | Working document? |  |  |  | Working document?
GRSP |  |  |  | GRSP May 2025 | WP.29 November 2025 | GRSP December 2025 | WP.29 March 2026 | GRSP May 2026 | WP.29 June 2026 | WP.29 November 2026
11 | Informal document | 2025-12-01 | P1 | Informal document |  | Working document |  |  | Working document
14 | Informal document | 2025-12-01 | P1 | Informal document |  | Working document |  |  | Working document
16 | Informal document | 2025-12-01 | P1 | Informal document |  | Working document |  |  | Working document
17 | Informal document | 2025-12-01 | P1 | Informal document |  | Working document |  |  | Working document
21 | Informal document | 2025-12-01 | P1 | Informal document |  | Working document |  |  | Working document
29 | Informal document | 2025-12-01 | P1 | Informal document |  | Working document |  |  | Working document
94 | Informal document | 2025-12-01 | P1 | Informal document |  | Working document |  |  | Working document
95 | Informal document | 2025-12-01 | P1 | Informal document |  | Working document |  |  | Working document
100 | Informal document | 2025-12-01 | P1 | Informal document |  | Working document |  |  | Working document
135 | Informal document | 2025-12-01 | P1 | Informal document |  | Working document |  |  | Working document
137 | Informal document | 2025-12-01 | P1 | Informal document |  | Working document |  |  | Working document
153 | Informal document | 2025-12-01 | P1 | Informal document |  | Working document |  |  | Working document
173 | Informal document | 2025-12-01 | P1 | Informal document |  | Working document |  |  | Working document
174 | Informal document | 2025-12-01 | P1 | Informal document |  | Working document |  |  | Working document
12 | TF-level draft (in preparation) |  | P2 |  |  | Working document |  |  | Working document
25 | TF-level draft (in preparation) |  | P2 |  |  | Working document |  |  | Working document
42 | TF-level draft (in preparation) |  | P2 |  |  | Working document |  |  | Working document
44 | TF-level draft (in preparation) |  | P2 |  |  | Working document |  |  | Working document
80 | TF-level draft (in preparation) |  | P2 |  |  | Working document |  |  | Working document
114 | TF-level draft (in preparation) |  | P2 |  |  | Working document |  |  | Working document
127 | Informal document |  | P2 | Informal document |  | Working document |  |  | Working document
129 | TF-level draft (in preparation) |  | P2 |  |  | Working document |  |  | Working document
134 | TF-level draft (in preparation) |  | P2 |  |  | Working document |  |  | Working document
145 | Informal document |  | P2 | Informal document |  | Working document |  |  | Working document
134 | TF-level draft (in preparation) |  | P2 |  |  | Working document |  |  | Working document
134 | TF-level draft (in preparation) |  | P2 |  |  | Working document |  |  | Working document
GTR1 | [7 empty] | Working document |  | Working document
GTR7 | [7 empty] | Working document |  | Working document
GTR9 | [7 empty] | Working document |  | Working document
GTR13 | [7 empty] | Working document |  | Working document
GTR14 | [7 empty] | Working document |  | Working document
GTR20 | [7 empty] | Working document |  | Working document
22 | [7 empty] | Working document |  | Working document
136 | [7 empty] | Working document |  | Working document
GRVA |  |  |  | GRVA January 2025 | GRVA June 2025 | GRVA September 2025 | WP.29 November 2025 | GRVA January 2026 | WP.29 March 2026 | WP.29 June 2026
R13 | Working document | 2025-06-01 | P1 | Informal document | Working document | Working document |  |  |  | Working document
R13-H | Working document | 2025-06-01 | P1 | Informal document | Working document | Working document |  |  |  | Working document
R79 | Working document | 2025-06-01 | P1 | Informal document | Working document | Working document |  |  |  | Working document
R140 | TF-level draft | 2025-09-01 | P2 |  |  | Informal document |  | Working document |  | Working document
R89 | TF-level draft | 2026-01-01 |  |  |  | Informal document |  | Working document |  | Working document
R90 | TF-level draft | 2026-01-01 |  |  |  | Informal document |  | Working document |  | Working document
R78 | [5 empty] | Informal document? |  | Working document |  | Working document
GTR8 | [5 empty] | Informal document? |  | Working document? |  | Working document?
R130 | [7 empty] | Working document |  | Working document
R131 | [7 empty] | Working document |  | Working document
R139 | [7 empty] | Working document |  | Working document
R152 | [7 empty] | Working document |  | Working document

## Feuil1
|  | GRVA 22 |  |  | GRBP 82 GRVA 23 | GRE 93 GRSG 130 GRPE 93 |  | GRSP 78 | GRVA 24 | GRBP 83 | GRPE 94 | GRE 94 GRSG 131 | GRSP 79
|  | WP.29 196 |  |  |  |  | WP.29 197 |  |  |  | WP.29 198 |  |  | WP.29 199
|  | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01
GRBP | R28 | bar: 2025-06-01 to 2025-11-01
R138 | bar: 2025-06-01 to 2025-11-01
R51 | bar: 2025-06-01 to 2025-11-01
R64 | bar: 2025-09-01 to 2026-02-01
R141 | bar: 2025-06-01 to 2025-11-01
R142 | bar: 2025-09-01 to 2026-02-01
R165 | bar: 2025-06-01 to 2025-11-01
GRE | R48 | bar: 2025-06-01 to 2025-11-01
R45 | bar: 2025-10-01 to 2025-11-01
R148 | bar: 2025-10-01 to 2025-11-01
GRPE | R83 | bar: 2025-06-01 to 2025-11-01
R154 | bar: 2025-10-01 to 2026-03-01
R24 | bar: 2025-10-01 to 2026-03-01
R68 | bar: 2025-10-01 to 2026-03-01
R49 | bar: 2025-10-01 to 2026-03-01
R115 | bar: 2025-10-01 to 2026-03-01
R143 | bar: 2025-10-01 to 2026-03-01
R168 | bar: 2025-10-01 to 2026-03-01
GRSG | R18 | bar: 2025-06-01 to 2025-11-01
R34 | bar: 2025-06-01 to 2025-11-01
R35 | bar: 2025-06-01 to 2025-11-01
R39 | bar: 2025-06-01 to 2025-11-01
R43 | bar: 2025-06-01 to 2025-11-01
R46 | bar: 2025-06-01 to 2025-11-01
R55
R58
R73
R93 | bar: 2025-06-01 to 2025-11-01
R97 | bar: 2025-06-01 to 2025-11-01
R102
R105 | bar: 2025-06-01 to 2025-11-01
R107 | bar: 2025-06-01 to 2025-11-01
R116 | bar: 2025-06-01 to 2025-11-01
R121 | bar: 2025-06-01 to 2025-11-01
R122 | bar: 2025-06-01 to 2025-11-01
R125 | bar: 2025-06-01 to 2025-11-01
R144 | bar: 2025-06-01 to 2025-11-01
R161 | bar: 2025-06-01 to 2025-11-01
R162 | bar: 2025-06-01 to 2025-11-01
R163 | bar: 2025-06-01 to 2025-11-01
R176 | bar: 2025-06-01 to 2025-11-01
R160 | bar: 2025-06-01 to 2025-11-01
R169 | bar: 2025-06-01 to 2025-11-01
GRSP | R11 | bar: 2025-06-01 to 2025-12-01
R14 | bar: 2025-06-01 to 2025-12-01
R16 | bar: 2025-06-01 to 2025-12-01
R17 | bar: 2025-06-01 to 2025-12-01
R21 | bar: 2025-06-01 to 2025-12-01
R29 | bar: 2025-06-01 to 2025-12-01
R94 | bar: 2025-06-01 to 2025-12-01
R95 | bar: 2025-06-01 to 2025-12-01
R100 | bar: 2025-06-01 to 2025-12-01
R135 | bar: 2025-06-01 to 2025-12-01
R137 | bar: 2025-06-01 to 2025-12-01
R153 | bar: 2025-06-01 to 2025-12-01
R173 | bar: 2025-06-01 to 2025-12-01
R174 | bar: 2025-06-01 to 2025-12-01
R12 | bar: 2025-12-01
R25 | bar: 2025-12-01
R42 | bar: 2025-12-01
R44 | bar: 2025-12-01
R80 | bar: 2025-12-01
R114 | bar: 2025-12-01
R127 | bar: 2025-06-01 to 2025-12-01
R129 | bar: 2025-12-01
R134 | bar: 2025-12-01
R145 | bar: 2025-06-01 to 2025-12-01
R146 | bar: 2025-12-01
R170 | bar: 2025-12-01
GTR1 | bar: 2026-05-01 to 2026-06-01
GTR7 | bar: 2026-05-01 to 2026-06-01
GTR9 | bar: 2026-05-01 to 2026-06-01
GTR13 | bar: 2026-05-01 to 2026-06-01
GTR14 | bar: 2026-05-01 to 2026-06-01
GTR20 | bar: 2026-05-01 to 2026-06-01
R22 | bar: 2026-05-01 to 2026-06-01
R136 | bar: 2026-05-01 to 2026-06-01
GRVA | R13 | bar: 2025-06-01 to 2025-11-01
R13-H | bar: 2025-06-01 to 2025-11-01
R79 | bar: 2025-06-01 to 2025-11-01
R140 | bar: 2025-09-01 to 2026-01-01
R89 | bar: 2025-09-01 to 2026-01-01
R90 | bar: 2025-09-01 to 2026-01-01
R78
| GTR8 | 2025-09-01: ID?; 2026-01-01: WD?
R130 | bar: 2026-01-01
R131 | bar: 2026-01-01
R139 | bar: 2026-01-01
R152 | bar: 2026-01-01