## Slide 1: Prioritized Items for Phase 3 of DCAS UN Regulation
SIM on highway, wHOR (EC, Industry)
SIM in urban environment, hands-on (EC, Industry)
SIM in other domains (e.g., roundabouts), hands-on (Industry)
SIM on highway-like roads (e.g., bicycles allowed), wHOR (Industry)
DCAS operation in closed parking areas at low speed (Industry)
Expanding lane change requirements for more natural driving experience (Industry)
TF on ADAS leadership ADAS-40-08

## Slide 2: Proposed Schedule & Deliverables (Indicative)
TF on ADAS 38th Session
30th Apr
Questionnaire distributed
Answers collected
23 May
Answers processed
first outcome to identify recommendations and gaps
Apr. 25 | May 25 | Jun. 25 | Jul. 25 | Aug. 25 | Sep. 25 | Oct. 25 | Nov. 25 | Dec. 25 | Jan. 26
TF on ADAS 39th Session
28th May
TF on ADAS 41th Session
37th Week
Draft
provisions agreed.
Informal document to GRVA-23
GRVA-23 22-26 Sep.
GRVA-24 19-23 Jan.
Working document to GRVA-24
GRVA-22 02-05 June
TF on ADAS 40th Session
30th Week
Further Discussions and agreements
Provisions first draft
Small Drafting Group:
To review recommendations and gaps collected
To judge whether the current provisions are enough
To identify whether additional evidence is needed
To identify whether additional research will be needed
Diversity of opinions
ADAS-38-04
ADAS-40-02
ADAS-40-03

## Slide 3: Topics for Consideration
ISMR
Audit
Monitoring of DCAS by the driver
Driver monitoring by DCAS
Attentiveness of the driver
Controllability
Reactiveness
System performance
HMI
Definitions