## Sheet1
Artificial Intelligence - Informal Working Group - Timeline
Week Number | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43
Week commencing: | time axis 2025-08-25 to 2026-06-22
Meetings
AI-IWG #1 - 27 Aug | bar: 2025-08-25
AI-IWG #2 - 2 Oct | bar: 2025-09-29
AI-IWG #3 - 13 Nov / 197th WP.29 | bar: 2025-11-10
AI-IWG #4 | bar: 2025-12-15
AI-IWG #5 - combine with GRVA? | bar: 2026-01-19
AI-IWG #6 | bar: 2026-02-09
AI-IWG #7 - combine with March WP.29? | bar: 2026-03-09
AI-IWG #8 | bar: 2026-04-06
AI-IWG #9 | bar: 2026-05-04
AI-IWG #10 - combine with GRVA? | bar: 2026-06-01
AI-IWG #11 | bar: 2026-06-22
WP.29 meetings | bar: 2025-11-10; 2026-03-09; 2026-06-22
ADS-IWG meetings | bar: 2025-10-13; 2025-12-08
GRVA meetings | bar: 2026-01-19; 2026-05-18; 2026-06-01
Task
6a - List of use cases
Gather initial input on example use cases | bar: 2025-08-25 to 2025-10-27
Compile information provided | bar: 2025-10-20 to 2025-11-03
Publish 1st draft AI-IWG use cases document | bar: 2025-11-10
Ongoing maintenance / update of document
6b - Literature review
Gather existing available relevant literature | bar: 2025-08-25 to 2025-11-10
Compile information provided | bar: 2025-09-29 to 2025-12-15
Publish 1st draft AI-IWG literature review | bar: 2025-12-15
Maintain and update document
6c - Develop guidance document
Develop initial draft terms & definitions document | bar: 2025-08-25 to 2025-11-10
Review existing literature to identify 'best practice' | bar: 2025-09-29 to 2025-12-15
Establish agreed structure / contents for document | bar: 2025-11-10 to 2026-01-19
Drafting Guidance Document - 1st draft | bar: 2026-01-19 to 2026-04-06
Reviewing / revising 1st draft | bar: 2026-04-06 to 2026-05-25
Presentation to GRVA | bar: 2026-06-01
Feedback from GRVA | bar: 2026-06-01 to 2026-06-15
Presentation to WP.29 | bar: 2026-06-22