## Roadmap
List of items for 08 series of amendments of UN Regulation No. 10 | [18 empty] | IWG-EMC-45-20
2024-11-29
N° | Proposal Source | Item | Ayhan's Summary | Reference | Sponsors | Lead | Progress Status: | Implementation timing | Support from CPs | [10 empty] | Comments (NGO views)
|  |  |  | Annex, paragraph |  |  |  |  | CN | CZ | DE | EC | FR | IT | JP | NL | SE | SP | UK
1 |  | ADAS and ADS considerations |  |  | FR/NL/EC | Remy Perot |  |  | Support from CPs JP: 47:Neutral
2 | IWG-EMC-46-04 IWG-EMC-47-17 | Radiated emission testing requirements - Below 30 MHz in driving mode | IWG-EMC-46-04: Expresses intention to propose Radiated emission testing requirements - Below 30 MHz (including charging mode) and in 1-6 GHz range - Further expanding vehicel operatign modes during emissions tests to consider 'normal conditions of use' IWG-EMC-47-17: Shares some test results form JRC in the 150kHz to 30 MHz range using CISPR36. Magnetic field, driving condition. Some emissiosn are present but below limits. |  | DE/EC | Thilo /DE JRC | Proposals received | UN R10.08 | Support from CPs JP: 47:Neutral | under development by JRC
2 | IWG-EMC-46-04 IWG-EMC-48-07 | Radiated emission testing requirements - Below 30 MHz in charging mode | IWG-EMC-48-07: Charge mode H-field measurement with setup mainly based on CISPR 36. Test setup deviated from R10. 6 Vehicles tested - all had emissiosn profile but none failed.Recommednation: Include test in R10. |  | DE/EC | Thilo /DE | Proposals received | UN R10.08 | Support from CPs JP: 47:Neutral
3 | IWG-EMC-46-04 | Radiated emission testing requirements in 1-6 GHz range | No concrete proposal recevied. CISPR/D WG1 working on CISPR 12 Edition 8 is developing the test method. Unikely to develop a credible proposal without a supporting standard |  | DE/EC | Thilo /DE |  | UN R10.08 | Support from CPs JP: 47:Do not support
4 | IWG-EMC-46-04 IWG-EMC-49-09 | Radiated emission testing requirements in variable driving condition | No concrete proposal recevied. CISPR/D WG1 • Work commenced on CISPR12- Possible additions Measurements extended to 6GHz – STF investigating methods Dynamic and variable speed testing Facility characterization Reverberation testing |  | EC | JRC |  |  | Support from CPs JP: 47:Neutral
5 | IWG-EMC-47-07 | Reverberation chamber for vehicle immunity test | OICA proposal submitted - what is needed to confirm? |  | NL/OICA/EC | OICA | Proposals received | UN R10.08 | Support from CPs CN: 47:Support; Support from CPs EC: 47:Support; Support from CPs JP: 47:Neutral; Support from CPs SE: 47:Support; Support from CPs SP: 47:Support; Support from CPs UK: 47:Support | OICA to prepare some proposal text
6 |  | Requirements for bi-directional charging | OICA is developing a proposal for next meeting |  | NL/OICA/EC | OICA |  |  | Support from CPs JP: 47:Neutral
7 | IWG-EMC-45-14-Rev.1 IWG-EMC-49-10 | Proposal for Simulation and Virtal Testing in UN R10 |  |  | NL/OICA/EC | OICA |  |  | Support from CPs JP: 47:Neutral
8 | IWG-EMC-48-06 IWG-EMC-49-06 | Electrostatic discharge (ESD) testing | NL experts believe ESD is applicable and should be added. Industry is opposing with |  | NL/EC | NL |  | UN R10.08 | Support from CPs JP: 47:Neutral
9 |  | AECS (e-call) during immunity testing | No proposal has been submitted |  | NL/EC | NL |  |  | Support from CPs JP: 47:Neutral
10 | IWG-EMC-38-05 | Reconsideration of whole vehicle approval based on ESA approvals only |  |  | NL/EC | NL |  |  | Support from CPs JP: 47:Neutral
11 |  | Dealing with software changes and versions Closed |  |  | NL/FR | Zissis /Ayhan |  |  | Support from CPs JP: 47:Neutral | Agreement in 45 meeting, item 6. Software changes should be managed in individual UN Regulations and not in UN R10 - Report IWG position back to GRE.
12 | IWG-EMC-45-10 IWG-EMC-46-16-Rev.1 | Replacement of pulse 4 reference | Implemented in Supplement 2 |  | NL | CLEPA/FR/SE | Proposals received | Supplement 2 to UN R10.07 | 46:Support | 46:Support | 46:Support | 47:Support | 46:Support | 46:Support | 46:Reserv. 47:Neutral 48:Support | 47:Support | 46:Support | 46: Abstain | 46:Support
13 |  | Inclusion of non-conductive charge modes | No proposal has been submitted |  | NL/EC | JRC |  |  | Support from CPs JP: 47:Neutral
14 |  | ADS suitability (screening of the Regulation) Task from GRE | OICA Proposal is under development. |  | GRE | OICA |  |  | Support from CPs JP: 47:Neutral
15 | IWG-EMC-48-03-Rev.1 IWG-EMC-48-04 IWG-EMC-48-05 IWG-EMC-49-02 | Upgrade radiated emissions testing to CISPR 12 Ed.7.0 | Adopds CISPR 12 7th edition. 20 dB customisation factor for BB emissions limited to ICE. 13dB for EV drive mode. No factor for charge mode. AG Comment: Could lead to confusion. Would it be clearer if Peak limits we explicitely listed in a table for categories 1, 2 and 3? |  | DE | Thilo /DE | Proposals received |  | Support from CPs JP: 47:Neutral
16 | IWG-EMC-47-15 | Remove peak detector use in conducted emission testing | in line with prior discussions - agreed |  | DE | Thilo /DE | Proposals received | UN R10.08 | Support from CPs JP: 47:Neutral
17 | IWG-EMC-47-03/04/14 | Precision of harmonics requirements (Annex 11) | Revise To: The vehicle shall be immobilized and in continuous charging mode., tThe engine(s) (ICE and / or electrical engine) shall be OFF. and in charging mode. |  | OICA | OICA/CLEPA | Proposals received | UN R10.08 | Support from CPs JP: 47:Support
18 | IWG-EMC-47-03/04/14 | Precision of flicker requirements (Annex 12) |  |  | OICA | OICA/CLEPA | Proposals received | UN R10.08 | Support from CPs JP: 47:Support
19 |  | Review and update of artificial networks (Appendix 8) |  |  | OICA | OICA |  |  | Support from CPs JP: 47:Support
20 | IWG-EMC-47-18 IWG-EMC-49-04-Rev.1 | Immunity related function list updates | IWG-EMC-47-18: Identified that about 30 regulations include EMC. Identified 4 new Immunity Related functions. Add 2 more test modes and 9 test conditions and failure criteria. IWG-EMC-49-04: Adds new immunity related functions (rear view camera systems, front and lateral view camera systems, moving off information systems and TPMS) Changes to failure criteria in Annex 6. |  | FR | FR |  |  | Support from CPs JP: 47:Neutral
21 |  | ESA homologation and test setup updates |  |  | FR | FR |  |  | Support from CPs JP: 47:Neutral
22 |  | Charging station simulator position in tests |  |  | FR | FR |  |  | Support from CPs JP: 47:Neutral
23 |  | Adaptive cruise control considerations |  |  | FR | FR |  |  | Support from CPs JP: 47:Neutral
24 |  | Low frequency magnetic fields (LMF) assessment for human body exposure |  |  | EC |  | Proposals received |  | Support from CPs JP: 47:Q1 Consider it outside the scope of R10. Q2 OEM | Consensus in the EMC-IWG-45 meeting: human exposure is not in the scope of R10
25 | IWG-EMC-45-03 | Fixed test harness length for vehicle level conducted emissions (Annex 13) | No progress since the start - awaitign test results. |  | OICA | OICA |  |  | Support from CPs JP: 47:Support
26 | IWG-EMC-45-04 | Removal of mode 2 REESS test modes | Objectiosn from Sweden and Spain. Italy said they did not want to discuss this any further. Withdraw? |  | OICA | OICA |  |  | Support from CPs JP: 47:Neutral
27 | IWG-EMC-46-11 IWG-EMC-49-07 | Introducing flowcharts for clarifying REESS test modes of ESAs | DO NOT support IWG-EMC-49-07: This is not just the case of converting what is written in current R10 to flowcharts but instead proposing significant test optimisations are proposed. (1) test in single or 3 phase (not both) (2) Test with one of IEC 61000-3-2 or IEC 61000-3-12 These are not supported by standards or R10.07 Need to hear further justifications |  | CLEPA |  | Proposals received | UN R10.08
28 | IWG-EMC-46-05 IWG-EMC-49-08 | Clarification of harmonics limits_IEC 61000-3-12 | Adding one more table to R10 to align with IEC 61000-3-12 which can be used in conditions d, e or f are met. Open topic: What to do when Rsce is >33 and customer has to do negotiate with grid operator…? What to write in used handbook? • OICA is neutral on this specific proposal. • Many experts expected a proposal consolidating requirements around a single Rsce=33. This would better ensure: universal grid compatibility, protected power quality, and a user-friendly charging experience. |  | CLEPA | CLEPA | No proposal received | UN R10.08 | Support from CPs FR: 46:Support | In Supplement 1 of UN R10.07, to come back to previous Edition. To decide to apply the proposal to UN R10.08 or in Supplement 2 of UN R10.07.
29 | IWG-EMC-46-09 IWG-EMC-46-15 IWG-EMC-47-12 | Clarification of Harmonics limits | IWG-EMC-46-09 - reasonable proposal, need to decide if it can be adopted IWG-EMC-46-15; informative only. Not a proposal IWG-EMC-47-12 JP response 46-15. Change 7.3.2.1 :If charging voltage is not covered within 220 to 240 V for single phase or 380 to 415 V for three phase, limit is modified to multiply by “230 / test voltage “ for single phase or “400 / test voltage “ for three phase.” |  | CLEPA | CLEPA | Proposals received | UN R10.08 | Support from CPs CZ: 46:Support; Support from CPs EC: 48:Neutral; Support from CPs FR: 46:Support; Support from CPs IT: 46:Support; Support from CPs UK: 46:Support
30 | IWG-EMC-46-07 | Clarification on flicker limits for ESA | Editorial : The dmax value for the flicker limit is clearly specified in the vehicle specifications but is not defined for ESAs, which could lead to ambiguity in interpretation. Therefore, it is proposed to set the value clearly at 6% to align with the vehicle limits. |  | CLEPA |  | Proposals received | Supplement 2 to UN R10.07 | Support from CPs FR: 48:Support; Support from CPs IT: 48:Support
31 | IWG-EMC-46-13-Rev.1 | Frequency-ranges_ESA |  |  | CLEPA |  | Proposals received | Supplement 2 to UN R10.07 | [11 empty] | 47: Agreement to be included in Supplement 2 of UN R10.07
32 | IWG-EMC-47-05 | Vehicle and ESA immunity - Editorial update of test level requirements |  |  | OICA | OICA | Proposals received | Supplement 2 to UN R10.07 | Support from CPs DE: 47:Support; Support from CPs FR: 47:Support; Support from CPs UK: 47:Support | 47: waiting for other Contracting Parties to decide.
33 | IWG-EMC-47-09-Rev.1 | Vehicle immunity - Update of ALSE method Update of standards' references |  |  | OICA | OICA | Proposals received | Supplement 2 to UN R10.07 | Support from CPs DE: 47:Support; Support from CPs FR: 47:Support; Support from CPs SP: 47:Support
34 | IWG-EMC-48-09 (option 1) IWG-EMC-48-11 (option 2) | Deletion of narrow broadband discrimination |  |  | CLEPA | CLEPA | Proposals received | UN R10.08
35 | IWG-EMC-49-12 | AC/DC Offboard charger |  |  | FR | FR | Proposals received | UN R10.08

## Drop down menus
Status: | Implementation timing
No proposal received | Supplement 1 to UN R10.07
Proposals received | Supplement 2 to UN R10.07
Implementation ready | UN R10.08 or Supplement 2 to UN R10.07
Highly Supported | UN R10.08
Rejected | UN R10.09
Accepted