## Sheet1
Open Issue Lists on A-LCA Working Document [ ]
The Latest Status
section | title | [ ] | as of 93rd GRPE | reference document | Status during 27th IWG meeting | who | what | by when | proposed text or the current status as of October 8 | After October 8th meeting Decisions | JPN positions <draft> | Justifications | OICA positions
all |  | light duty vehicle | CLOSED @ 27th IWG mtg | NA | agreed with "LDV" the modified text for functional unit is expected to be present during 28th IWG meeting (October 8th) | SG4 | consult with the relevant member and develop the compromised text for FU, then sent to IWG leading team | 2025-10-03 | for functional unit, please refer III 7.5. |  | support "light duty vehicle" instead of "passenger car" including the modification of functional unit please refer A-LCA-26-06r1e
|  | phase vs stage | CLOSED | NA | CLOSED with "stage" for each life cycle |  | DONE |  |  |  | please refer A-LCA-26-07e
| Inconsistency in equations | newly propposed @ 27th IWG mtg | OPEN | A-LCA-27-08e_OICA_UNECE A-LCA method TEST formula.xlsx | newly proposed | OICA | propose the solution and send to the relevant SG | 2025-10-03 | no action is taken | to be concluded IWG 29th meeting |  |  | A-LCA-27-06e A-LCA-27-08e
III 1.1. | Purpose and principles | and verification | CLOSED | NA |  | IWG | will make a decision on 10/8 | 2025-10-08 | Leading Team Decision remove [ ] | remove [] adopted | keep "and verification"(Japan comment) | concern on cheating without verification
III 3. | Definitions |  | OPEN on several items | GRPE-93-43 |  | SG7 | DONE |  | several [ ]s remain | skipped | basic idea : no terminology or well described in the text→delete、inconsistant with the text→modify or delete concrete proposals : later
III 7.1 | Level Concept | texts in [ ] | CLOSED except Table 1 | GRPE-93-43 | CLOSED except USE stage in blue highlighted portions final confirmation on A-LCA-26-04r1e_GRPE-2025-17 Draft ID_Level Concept after 26th Mtg.docx including the proposal made by SG2 confirm the final modification within 27th A-LCA-27-10e | SG3 SG7 | under the progress |  | close to finalisation by SG7 with huge support from Song-san | skipped
Figure 1
Figure 2
|  | Table 1 | [7 empty] | [] to be modified after SGs update
III 7.3 | Hotspots | texts in [ ] | OPEN | [5 empty] | designated group proposal : A-LCA-28-03e OICA input : A-LCA-28-03e |  | tbd |  | A-LCA-27-07e
|  | Figure 3 (bottom table) |  | 251023_clean GRPE-2025-XX Draft Informal Document BASIS FOR COMMENTS FOR GRPE WEEK-hotspot.docx 251006_clean GRPE-2025-17 Draft Informal Document_Hotspot.docx | the designated group* is set to develop the compromised proposals * : USEPA/France/SG3/OICA next action : IWG leading team will organise the | A-LCA leading team | consult with the relevant member and develop the compromised text | 2025-10-03 |  | Maintain original 3.33 with OICA additional text. 7.3 should be kept but moved to another part of MR because it's general information. Hotspot to be further developed in IWG 29 US EPA to lead discussion week 41 with JPN, OICA, EU COM, CLEPA | All life cycle [stages] collectively contributing more than 50% to any impact category. With this definition, one specific process contributing 49% of impact within a certain life phase may not be pursued as a “Hot spot”? should be consider per each life cycle stage considering the consistency with cut-off rule [50%] is still open |  |  | Hotspot means a certain process which emits higher amount of GHG exceeding the average in a certain boundary condition.
III 7.5 | Functional Unit and reference flow | texts in [ ] | OPEN | A-LCA-SG4-31-05_GRPE-2025-17 Draft Informal Document_SG4_FU.docx | [ ] waiting for SG4 meeting outcome | SG4 | consult with the relevant member and develop the compromised text, then sent to IWG leading team | 2025-10-03 | A-LCA-28-09e | to be forwarded to SG7 | please refer A-LCA-26-06r1e
III 7.8 | Land Use Change | texts in [ ] | OPEN | NA | (SG6) | SG6 | provide the SG6 decision to IWG leading team | 2025-10-03 |  | CP meeting before 29th IWG | no strong position |  | A-LCA-27-07e
III 7.9 | Representative vehicle (RV) Determination | texts in [ ] | OPEN | A-LCA-28-11e_GRPE-2025-17 Draft ID_RV.docx | 1. definition of upstream group criteria is expected to be present during 28th IWG meeting 2. need further explanation to US/JRC for better understanding | SG3 | develop the compromised text based on the agreement with the relevant member (currently USEPA is arranging the designated meeting) | 2025-10-03 | new proposal is under the review by the designated group (meeting data : tbd) | meeting with OICA JPN, JRC, US EPA before 29th IWG | please refer the sheet ”RV” and please refer A-LCA-28-11
III 7.9.2 | RV: Selection | the highest configuration of a vehicle | [8 empty] | not acceptable please refer A-LCA-26-08e/09e | avoid cheating
III 7.9.3.1. | Definition of Upstream LCA Group | (a) | [8 empty] | delete all and describe (reserved) at this stage please refer A-LCA-26-08e/09e | current criteria makes no sense. Please refer the sheet "RV". No concrete counter-proposal is available | A-LCA-27-07e
(b)
(c)
(d)
III 7.9.6.1. | Definition of EoL LCA group | [9 empty] | delete all and describe (reserved) at this stage please refer A-LCA-26-08e/09e
III 7.12. | Data collection requirements and data types |  | OPEN deadline of comments : 10/27 | GRPE-2025-17 Draft ID_Data Quality_PDS including EC comments.docx | keep as it is with [ ] | SG3 | consult with the relevant member and develop the compromised text, then sent to IWG leading team | 2025-10-03 | under the discussion within SG3 and relevent member
|  | Table 2 | [8 empty] | Use and EoL should be added in the same manner of material and production should include Use and EoL stages
III 7.12.1. | Data quality | most |  |  | keep as it is with [ ] | [6 empty] | ambiguous
III 7.12.2. | Primary data share | 50% |  |  | keep as it is with [ ] |  |  |  |  | before 29th IWG CP & SG4 to confirm or reject 50% PDS in production SG3 to provide updated text to A-LCA leading team for distribution to IWG wiki | oppose(Japan comment) not acceptable | 1. may disturb decarbonisation in some cases (original text mentioned, but seem to be intentionally deleted) 2. waste a ton of resources to determine and/or track so many materials and parts with no contribution on decarbonisation. these resources should be utilise the real decarbonisation 3. leads to kick out the small manufacture from market. against the economic principle and customer benefit 4. industry accelerate the primary data usage to pursue their product without PDS 5. make no sense as a methodology | A-LCA-27-06e A-LCA-27-07e |  | PDS=33%? | 78.4% | real world FE = xx L/km（P） * 1.25（descrepancy_S） * 1.02（deterioration_S）
[15 empty] | PDS=67%? | 98% | real world FE = xx L/km（P） * 1.25（descrepancy_P） * 1.02（deterioration_S）
III 7.13. | Cut-off rule | 3% | CLOSED | NA | keep as it is with [ ] | Leading Team | provide the Leading Team decision and gather IWG member feedbacks | 2025-10-03 | Leading Team Decision remove [ ] no proposal other than JPN | [] to be removed | ok(Japan comment) acceptable
III 7.14. | Screening Analysis |  | OPEN OICA provide the modified text by 10/27 | NA | waiting for OICA input by 24th September | OICA SG3 | OICA provide their concerns to SG3, then SG3 develop the compromised text | 2025-10-03 | no action is taken | OICA to respond to CLEPA to explain concerns before 29th IWG |  |  | A-LCA-27-07e
III 7.15.2. | Electricity modelling | [The inclusion of such upstream elements should be prioritised ....] | OPEN discussion table is shared within SG6 deadline 10/26 | 20251009_SG6_Comments_CPs_Leader_EC_FR_US_UK_DRAFT_JRC.xlsx | in progress | SG6 | provide the SG6 decision and inform IWG leading team of their decision | 2025-10-03 |  | CPs request to respond to SG6 leaders and next meeting still to be scheduled COM to present COM view on IWG 29 meeting and Wiki US to organise meeting with CPs Week 41 | no strong position | can be deleted since defined in the other section
III 7.15.2.1. | Electricity from the grid via a contractual instrument | • [Mixing location-based and market-based modelling shall be avoided within one life cycle [stage] of an LCA]. |  |  | in progress | [7 empty] | A-LCA-27-07e
|  | [The entity shall document in the carbon neutrality management plan...] |  |  | in progress | [6 empty] | no strong position
III 7.16.2.4 | Multi-output allocation | economic value ratio is equal to or lower than five | OPEN | Multi Output Allocation_20251008.pdf | keep as it is with [ ] | SG3 | consult with the relevant member and develop the compromised text, then sent to IWG leading team | 2025-10-03 | under the discussion with SG3 and relevent member | CPs invited to check text before 29th IWG. SG3 request to provide justification and examples to be shared with A-LCA IWG leading team |  | not acceptable The decision to adopt physical or economic allocation is based on the economic ratio, though this is not an ISO rule. ISO simply prioritizes allocation methods based on physical relationships (e.g., weight), followed by other relationships (e.g., economic value). The A-LCA methodology should follow this order as well. Consequently, Figure 12 and the related text must be amended.
|  | If physical relationships are not used, the validity of the allocation method used in the study should be demonstrated |  |  | keep as it is with [ ] | [5 empty] | OK to delete [ ] (support the text) | proposed by Japan (follow ISO rule)
III 7.17. | Chain of custody |  | CLOSED | GRPE-93-43 | Next actions : IWG leading team will invite CP for their concrete position (items not to be supported,,,) until 28th IWG meeting text : additional texts need to be readable JPN/CLEPA and US provide the concrete text proposals, then come back for further discussion on Day2 waiting for counter-proposal on A-LCA-26-05e come back at 14:30CET for integrated document by US/JPN/CLEPA | SG2 SG3 | consult with the relevant member and develop the compromised text, then sent to IWG leading team | 2025-10-03 | new text was developed for IWG review A-LCA-28-03e | Content confirmed by IWG. Draft to be updated and shared with SG7 | please refer A-LCA-28-08e_GRPE-2025-17 Draft ID_SG7_CoC_Modified_d5 | one of major contributors for green washing
III 7.18. | Waste treatment, disposal and recycling modelling | GHG emissions shall be calculated… | CLOSED | GRPE-93-43 | CLOSED with A-LCA-27-05e | Leading Team | confirm the A-LCA-27-05e document and upload the document | 2025-10-03 | need to be implemented into the Informal Document (delete text and [ ] ) | [] removed and closed |  |  | A-LCA-27-06e A-LCA-27-07e
III 8.1. | [12 empty] | A-LCA-27-07e
III 8.1.6. | Energy modelling | For the general rules reference is made to paragraph 3.2.15. In case of electricity supply from the grid and marked based energy modelling (Level 4 & hotspots in Level 3) the following rules shall apply: • If no contractual instruments are applied the residual electricity mix shall be used if available. • If no residual grid mix is provided, secondary data shall be applied reflecting the country specific grid mix. For Level 3 and partially Level 4 the risk of double counting cannot...] | OPEN | 20251009_SG6_Comments_CPs_Leader_EC_FR_US_UK_DRAFT_JRC.xlsx | (SG6) | SG6 | consult with the relevant member and develop the compromised text, then sent to IWG leading team | 2025-10-03 |  |  | support original text | For general rules refer to paragraph 3.2.15. 4.1.4.1. Energy Mix Practitioners shall account for the fuel or electricity production pathways associated with the production locations of each material. (detailed methodology shall be considered) The energy mix shall be based on the latest dataset associated with the location or region of production in question. The methods described in paragraph 3.2.8. shall guide the modelling of fuel and electricity for these regions.
III 8.2. |  |  | OPEN | A-LCA-27-07e_OICA Testing summary 16 Sept 2025.xlsx | (SG3) | OICA | provide the concrete proposal to the relevant SG | 2025-10-03 | no action is taken | to be solved. Text to be shared with IWG A-LCA leading team > to SG 7 |  |  | A-LCA-27-07e
III 8.2.1.1. | Level 1 |  | OPEN | NA | (SG3) | SG3 |  |  | no action is taken | to be solved. Text to be shared with IWG A-LCA leading team > to SG 7
III 8.2.1.3. | Level 3 |  | OPEN | NA | (SG3) | SG3 |  |  | no action is taken | to be solved. Text to be shared with IWG A-LCA leading team > to SG 7
III 8.3. |  |  | OPEN | A-LCA-27-07e_OICA Testing summary 16 Sept 2025.xlsx | (SG4) | OICA | provide the concrete proposal to the relevant SG | 2025-10-03 | no action is taken |  |  |  | A-LCA-27-07e
III 8.4.] | [Service life/Vehicle activity] and functional unit |  | OPEN | A-LCA-SG4-31-05_GRPE-2025-17 Draft Informal Document_SG4.docx | (SG4) | SG4 | consult with the relevant member and develop the compromised text, then sent to IWG leading team | 2025-10-03 | A-LCA-28-09e | Closed
III 8.3.1.1. | Service life: methodology and guideline | can indicate a shorter service life supported by primary data, which will lead to a more stringent functional unit | OPEN |  | (SG4)
III 8.3.3. | Use phase consumption | OEM-specific average data may be used to determine the “Discrepancy factor” | OPEN |  | (SG4) | [5 empty] | not acceptable (JPN has already provided the counter-proposals) | OEM specific factor may lead cheating
|  | powertrains with two modes of operation | OPEN
|  | Table 11 | OPEN
|  | non-CO2 exhaust emissions | OPEN
III 8.3.3.1. | Calculation of ‘Discrepancy Factor’ | Table 13 | OPEN |  | (SG4) | [5 empty] | not acceptable (JPN has already provided the counter-proposals) | OEM specific factor may lead cheating
III 8.3.3.2. | Calculation of ‘Deterioration Factor’ |  | OPEN |  | (SG4) | [5 empty] | not acceptable (JPN has already provided the counter-proposals) | technically make no sense to distinguish between discrepancy and deterioration under the current OBFCM accuracy
III 8.3.3.3. | Quantification of Leakages |  | OPEN
III 8.3.5.1. | Future Changes in Energy Mix: | a static scenario may be used only where a dynamic scenario is not available | OPEN |  | (SG4) | [5 empty] | allow Static？
|  | future scenarios issued… | OPEN | [7 empty] | no strong position
III 8.3.5.2. | Use phase electricity: |  | OPEN |  | (SG4) | [5 empty] | no strong position | delete reinstate）
III 8.3.6.2.3. | Determination of Frequency |  | OPEN |  | (SG4) | [5 empty] | not acceptable (JPN has already provided the counter-proposals) | depend on reality in the market
III 8.3.6.2.4. III 8.3.6.2.6. | traction battery and fuel cell system replacement |  | OPEN | [7 empty] | not acceptable (JPN has already provided the counter-proposals) | depend on reality in the market
III 8.4. |  |  | OPEN | A-LCA-27-07e_OICA Testing summary 16 Sept 2025.xlsx | (SG5) | OICA | provide the concrete proposal to the relevant SG | 2025-10-03 | no action is taken | solved |  |  | A-LCA-27-07e
III 9. | Reporting |  | OPEN | A-LCA-28-05e_GRPE-2025-17 Draft ID_Reporting for SG2_3_4_5.docx | CLOSED on SG2/3/5 portions more discussion is necessary for other portions and should be reviewed during the 28th IWG meeting | Leading team | consult with SG3/4 and provide the compromised text to IWG member | 2025-10-03 | A-LCA-28-09e need to be revised per CoC modification | Updated text to be provided by IWG29 with COC changes | please refer please refer A-LCA-26-03e
III 10. | Verification process | For Level 3 and 4, the verification … | OPEN | 201024_GRPE-93-43e_clean_verification.docx | waiting for OICA input by 24th September | OICA | provide the concrete proposal to the relevant SG | 2025-10-03 | A-LCA-28-10e OICA input for IWG review | Delete [] text to be forwarded to SG7 |  |  | A-LCA-27-07e
In the case that no verification body…

## timeline
|  |  |  | October, 2025 |  |  |  |  | March, 2026
|  | 2025-07-22 |  | 93rd GRPE |  | 2025-12-12 | end of 2025 |  | WP.29 | 94th GRPE
Current | Mandate
GRPE Approval
WP.29 Approval
Reviced Plan | Case_1
| Mandate | [5 empty] | no need to change the mandate
| GRPE Approval |  |  |  |  | WD deadline |  |  |  | ToR needs to be modified
| WP.29 Approval | [9 empty] | November, 2026
Case_2
| Mandate | [7 empty] | Mandate needs to be modified
| GRPE Approval | [7 empty] | update WD by ID | ToR needs to be modified
| WP.29 Approval | [9 empty] | November, 2026
Case_3
| Mandate | [5 empty] | no need to change the mandate
| GRPE Approval |  |  | with reserved on some parts
| close "reserved parts" |  |  |  |  | WD deadline |  |  |  | ToR needs to be modified
| WP.29 Approval | [9 empty] | November, 2026
EU guideline
X year extention
[7 empty] | finalise the first stage activities |  | develop second activities like testing
| GRPE Approval |  |  | NONE | [5 empty] | with no reserved parts
submit ID reflected the latest situation
or submit ID reflected only agreed items
[6 empty] | close the open items* |  |  | items can be taken care in second phase and by when
[5 empty] | * | energy modeling |  |  |  | representaative vehcile (detail)
hotspot
representaative vehcile (concept)
date quality and primary data share
use stage
|  |  | EC | no text available to be voted @ 93rd GRPE
US
JPN

## timeline(detail)
[6 empty] | Oct |  | Nov |  |  |  |  | Dec
[6 empty] | Week43 | Week44 | Week45 | Week46 | Week47 | Week48 | Week49 | Week50
[6 empty] | Sun(19) | Sun(26) | Sun(2) | Sun(9) | Sun(16) | Sun(23) | Sun(30) | Sun(7)
|  |  | concept | draft text | on New reference doc based on GRPE-93-43 or separate doc | Nov Week45 Sun(2): 6th Nov. ALCA(30); Nov Week46 Sun(9): (WP.29); Nov Week47 Sun(16): xth Nov. ALCA(31); Nov Week49 Sun(30): xth Nov. ALCA(32) ?
SG1 | all | Inconsistency in equations | CLOSED
| III 1.1. | Purpose and principles | CLOSED
| III 3. | Definitions
| III 7.1 | Level Concept |  | Modification on "Table 1" ? |  | Nov Week45 Sun(2): Close
| III 7.3 | Hotspots |  | 251023_clean GRPE-2025-XX Draft Informal Document BASIS FOR COMMENTS FOR GRPE WEEK-hotspot | New reference doc based on GRPE-93-43 | Nov Week45 Sun(2): Close
| III 7.5 | Functional Unit and reference flow | CLOSED
| III 7.8 | Land Use Change |  | to follow SG6 |  | Nov Week47 Sun(16): Close
| III 7.9 | Representative vehicle (RV) Determination |  | "20251002_GRPE-2025-17 Draft ID_SG7_RV.docx" from OICA as of 3rd Oct. | separate doc | Nov Week45 Sun(2): Close
| III 7.9.2 | RV: Selection |  | (see "III 7.9.")
| III 7.9.3.1. | Definition of Upstream LCA Group |  | (see "III 7.9.")
| III 7.9.6.1. | Definition of EoL LCA group |  | (see "III 7.9.")
| III 7.12. | Data collection requirements and data types |  | "(DQ_PDS)GRPE-2025-17 Draft ID_SG7 (003).docx" from CLEPA as of 14th Oct. | separate doc | Nov Week45 Sun(2): Close
| III 7.12.1. | Data quality |  | (see "III 7.12.")
| III 7.12.2. | Primary data share |  | (see "III 7.12.")
| III 7.13. | Cut-off rule | CLOSED
| III 7.14. | Screening Analysis |  | OICA to respond to CLEPA to explain concerns before 29th IWG | New reference doc based on GRPE-93-43
| III 7.15.2. | Electricity modelling |  | to follow SG6 |  | Nov Week47 Sun(16): Close
| III 7.15.2.1. | Electricity from the grid via a contractual instrument |  | to follow SG6 |  | Nov Week47 Sun(16): Close
| III 7.16.2.4 | Multi-output allocation | OPEN | no change from "ECE/TRANS/WP.29/GRPE/2025/17" |  | Nov Week45 Sun(2): Close
| III 7.17. | Chain of custody | CLOSED | GRPE-93-43 | New reference doc based on GRPE-93-43
| III 7.18. | Waste treatment, disposal and recycling modelling | CLOSED | GRPE-93-43 | New reference doc based on GRPE-93-43
| III 9. | Reporting |  | Updated text to be provided by IWG29 with COC changes | New reference doc based on GRPE-93-43 | Nov Week45 Sun(2): Close
| III 10. | Verification process | CLOSED? | "201024_GRPE-93-43e_clean_verification.docx", GRPE-93-43 modifyed by Korea | New reference doc based on GRPE-93-43 | Nov Week45 Sun(2): Close
SG2 |  |  |  | SG7 meeting on 29th Oct |  | Nov Week45 Sun(2): Close
SG3 |  |  |  | SG7 meeting on 30th Oct |  | Nov Week45 Sun(2): Close
SG4 |  |  |  | To confirm the insertion of CONCAWE's inputs |  | Nov Week45 Sun(2): Close
SG5 |  |  |  | SG7 meeting on 29th Oct |  | Nov Week45 Sun(2): Close
SG6 |  |  |  | SG7 meeting on 30th Oct |  | Nov Week47 Sun(16): Close
week43 : Invite SG1 related open issues and closed issues
week44 : Invite SGx related issues
Early half of week 45: compile all inputs
IWG meeting on 6th : the IWG can review the compile doc at that timing