## Blad1
DETA-27-08e
| Functionalities | User | Role | Responsibility | Budget | Status | Impl. date | Kosten | effort [PDs] | Who?
existing | constraint: current TypMaster release |  |  |  | funded by UNECE | in progress |  | Lizenz TypMaster 30K€
| up-/downloading of approval documents | by approval authorities | user | CP's applying min. ?? ECE Regs | 30T€
| setup and manage acces rights | by type approval holder (mnf's) | by administrator | KBA/UNECE | 0 | open |  |  | 20 | 3 persons each 5 days (KBA, Software house; OEM) and 5 days one person
| mandatory attributes in current release is sufficient | [7 empty] | 1 | Software house
to develop
1 | initial set up KBA/UNECE |  | database administrator | tool administrator |  | open | KBA |  | 2 | KBA and Software house
2 | transition KBA to UNECE |  | software house | tool administrator |  | open | KBA/UNECE
introduction of UI:
3 | - migration of already uploaded approval docs (for step 0 docs: use ID as UI) | administrator | database administrator | tool administrator | 0 | open | KBA |  | 3 | KBA and Software house
4 | - manage UI's | type approval authority | software house | software house | 35T€ | Unique Identifier for multiple approvals | T-Systems
5 | - link new UI to set of type approvals/UI's (new template?/user interface?) | type approval authority | type approval authority (on req. mnf) | type approval authority | 0 |  |  |  |  | each TAA has to deliver this task
6 | - search function by UI: | - CP's, access to type approvals | tool administrator | tool administrator | 0 |  |  |  | 5 | KBA
7 |  | - open to public, to type approval numbers only | tool administrator | tool administrator | 0
8 | new attributes |  | software house | software house | 25T€ | Additional archive attributes
9 | manage list of mnf's | by administrator | tool administrator | tool administrator | 40T€ | Roles and rights (Manufacturer Entity)
introduce IWVTA:
10 | - add attribute: IWVTA class + IWVTA type | may be automatically generated from TA number? | software house | software house | 25T€ | Import IWVTA
11 | introduce DoC:
12 | part 1: upload function for VIN's with appr.no; create the R0 Annex 6 App1 form: | by CP (based on input from mnf IWVTno+VIN) | manufacturers | manufacturers | 80T€ | Assign VIN to the corresponding approval
13 | part 2: creation function tbd based on use cases | investigate use cases | tbd (type approval authorities or mnf's) | tbd (type approval authorities or mnf's) | 80T€ | Generate document of conformity (DOC)
14 | transfer access rights by type approval holders to other parties then authorities |  | type approval holder | type approval holder | 15T€ | Support transfer
[9 empty] | 0,4PY | KBA ongoing administration