## Slide 1: PMP – PN sub 23nm
Route to transfer from ‘in case of urgent need’ into planned delivery into regulations
PMP-48
Presentation from Technical Secretary

## Slide 2: Background
PMP tasked to develop sub-23nm procedure ‘in case of urgent need’.
PMP continues to develop sub-23nm procedure and to monitor new technologies – to date, still no urgent need.
PMP should develop a roadmap to move sub-23nm into regulation in a routine way ready for adoption in next major regulatory updates.
PMP will need to incorporate this in the request in 2019 for prolongation of the mandate and have a clear work plan defined for the next 3 years.

## Slide 3: Objectives
Route to transfer from ‘in case of urgent need’ into planned delivery into regulations

## Slide 4: Current Status sub-23nm
Round Robin started end 2017
Testing on-going - labs in Europe / Asia
Round Robin Report mid 2018
PMP current position
  Technically feasible in principle to move to sub-23nm – i.e. D50 10nm if calibration protocols can be be developed. Further move to D50 lower than 10 not recommended due to significantly high uncertainties.
Remains necessary to test Euro 6d technologies as well as new / emerging technologies (eg GDI with GPF, CNG HD / LD and extension to Gasoline MPI & PFI)

## Slide 5: Next Steps sub-23nm
Review RR outcome
Clear review of uncertainties inside a lab (repeatability) and between labs (reproducibility) and delta between 23 and sub-23 nm methods by technology – light duty and heavy duty, propose procedure / sampling refinements
Test new / emerging technologies (eg Euro 6d GDI with GPF, HD CNG engine, LD CNG, PFI, regeneration measurement)
Clear description of equipment changes needed from today 23nm measurement to sub-23nm capability
Updated calibration procedure needed for lower cut off size
Consider clarification of calibration procedures to set up a more consistant approach by instrument manufacturers
When is the right time to change calibration material from emery oil to soot / silver ? PMP leadership team recommends at next regulation change not as running change to existing setup

## Slide 6: Next steps continued
Review RDE measurement equipment for alignment with sub-23nm procedure (uncertainties),
Particle pre-treatment – VPR or CS decision needed.
Propose adaptations of equipment where needed and better definitions of procedures
Impact of heavy fuels on PN results – determine if sensitivity to sub-23nm different to 23nm procedure
Verification study to confirm adaptations on sampling / measurement procedure / calibration. Determination of uncertainties / losses – possible correction methods, reproducibility / repeatability WLTP in lab (23 deg C, 14 deg C, winter temperature test, regeneration)
PMP establish correlation for sub-23nm limit values giving equivalent stringency to current 23nm limits in EU.
Futher test prog required

## Slide 7: Open Questions & External Activities
Linkage with RDE PN procedure / calibration ?
Need to avoid different calibration protocols for WLTP and RDE PN measurement systems ?
PMP should consider if/how to contribute to technical knowledge on PN PEMS sub-23nm including calibration recommendations and CF + error margin recommendations
Outcome of Horizon 2020 projects – systems ?
Futher test prog required

## Slide 8: Potential timeline /Milestones
 |  | 2019 |  |  |  | 2020 |  |  |  | 2021 |  |  |  | 2022 |  |  | 
 |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Calibration material and CPC efficiency
VPR or CS
Study with calibration material, challenging all ICE concepts – HD / LD including regeneration
Sampling
Adaptations and particle loss determinations
Calibrations guidelines
Verification study
Draft decision Soot, silver or emery oil
Proposed system/procedure to determine
Uncertainty
Measurement data from all concepts to support revised sub-23nm limit values – including regeneration and durability
draft
final
Fuels / PN study
Limit value recommendation, including DF and Ki
Study on heavy fuel impact
Analyse data, determine correlated limit values for sub-23nm at equivalent stringency to existing PMP method for HD and LD
Final decision on procedure / sampling set up
Needs to work for RDE too
Final decision Soot, silver or emery oil
Metrology institutes input required
Preliminary decision on procedure / sampling set up

## Slide 9: Potential timeline /Milestones
 |  | 2021 |  |  |  | 2022 |  |  |  | 2023 |  |  |  | 2024 |  |  | 
 |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Regulation drafting
Lab implementation
Allowance of sub-23nm procedure as alternative with correlated limit values
Draft UN reg
publication
Availability of equipment, training, calibration resources etc