## Sheet1
Informal Document EVE-06-03e
Revised EVE Roadmap - May 2013
|  | start date | end date | status | EVE-01 | -- | EVE-02 | EVE-03 | -- | EVE-04 | -- | EVE-05 | EVE-06 | -- | EVE-07 | -- | EVE-08 | EVE-09 | -- | EVE-10 | -- | --
| Task |  |  |  | 2012-06-01 | 2012-06-01 | 2012-09-01 | 2012-11-01 | 2012-11-01 | 2013-01-01 | 2013-03-01 | 2013-04-01 | 2013-06-01 | 2013-06-01 | 2013-10-01 | 2013-11-01 | 2014-01-01 | 2014-02-01 | 2014-03-01 | 2014-06-01 | 2014-06-01 | Nov-14
[5 empty] | GRPE | WP.29 | USA | Webex | WP.29 | GRPE | WP.29 | Japan | GRPE | WP.29 | China | WP.29 | GRPE | TBD | WP.29 | GRPE | WP.29 | WP.29
1 | Adopt EVE Terms of Reference | 2012-06-01 | 2012-09-01 | completed
1.1 | Submit to GRPE |  |  | completed
1.2 | Submit to WP.29 (expect: June 2013)
2 | Exchange of information (regulatory frameworks, other IWG, etc,…)
2.1 | Research and information sharing | 2012-06-01 |  | on-going
2.2 | Discuss potential research gaps and agree on test plan | 2013-04-01 | 2013-10-01 | started
2.3 | Conduct research/test plan | 2013-10-01 | 2014-06-01
3 | Reference Guide Development
3.1 | Establish list of vehicle attributes | 2012-11-01 | 2013-01-01 | completed
3.2 | Develop questionnaire | 2012-11-01 | 2013-01-01 | completed
3.3 | Send questionnaire to EVE members (after EVE-04) | 2013-02-01 | -- | completed
3.4 | EVE & GRPE members fill-in questionnaire | 2013-02-01 | 2013-04-01 | completed
3.5 | Compile information into report | 2013-04-01 | 2013-12-01 | started
3.6 | Develop recommendations on potential future gtr development | 2013-04-01 | 2013-12-01
3.7 | Circulate 1st draft Reference Guide to EVE for comments |  | Sept. 30
3.8 | Revise Draft Reference Guide based on EVE comments | 2013-10-01 | Dec. 1
3.9 | Submit 2nd draft to GRPE for comments (submit a few weeks before) | -- | Dec. 1
4 | Revise Draft Reference Guide based on GRPE comments | 2014-01-01 | March. 1
4.1 | Submit 3rd draft Reference Guide to GRPE (submit >12 weeks before) | -- | March.1
4.2 | Approval of Reference Guide by GRPE | -- | 2014-06-01
4.3 | Submit Reference Guide to WP.29 (submit >12 weeks before, Secretariat's duty) | -- | Aug. 1
4.4 | Approval of Reference Guide by WP.29 | -- | 2014-11-01
-- | Current EVE mandate ends (summary report of activities)
prepared by: EVE Secretary, May 2013