## Slide 1: WLTP IWG 26th Session 15th - 18th April 2019 Status Report from UNR WLTP Transposition Task Force
WLTP-26-10e

## Slide 2: Post-25th WLTP IWG Update
78th GRPE Geneva, January 2019
  Agreement to delay UNR WLTP Working Document by one GRPE session – submission to UNECE in October 2019 for 80th GRPE in January 2020
  GRPE recognised the urgency for the task force to work on the definition of the most stringent, harmonized level (Level 2)
  Japan and EC both agreed with the objective of harmonisation
  OICA supported harmonisation, but stressed the need for the UNR to be technically and economically feasible
February/March – bilateral meetings between EC and MLIT
  Updates made towards harmonisation of issues/topics where there are currently regional options – revised document prepared for discussion at Transposition Task Force and 26th WLTP IWG

## Slide 3: Post-25th WLTP IWG Update
  3rd April 2019 – Transposition Task Force meeting, Tokyo
  Further discussions on regional options – to be continued at 26th WLTP IWG. Discussions on Durability test – to be continued at 26th WLTP IWG
UNECE Wiki page created:
https://wiki.unece.org/pages/viewpage.action?pageId=81888039

## Slide 4: 26th WLTP IWG and beyond
26th WLTP IWG
  Further discussions on harmonisation, including Durability and COP
  Review of draft regulatory texts
  Discussions/agreement on specific technical elements, including amongst others:
    Dual-axis dyno – restraint and ALR test
    Target speed correction
  Task Force meeting planned for 8th May 2019
  Drafting of UNR WLTP text
Informal documents to be submitted to 79th GRPE (May 2019)
  UNR WLTP and UNR83 08 Series
    With square brackets and holding comments as appropriate (e.g. for COP where it is unlikely that draft requirements will have been agreed by GRPE)

## Slide 5
Contact information
Rob Gardner, TRL Ltd on behalf of the European Commission (Task Force Leader)
rgardner@trl.co.uk