## Slide 1
Draft of states report to GRBP #71
Chair of Task Force on Reverse Warning Sound issues

## Slide 2
Meeting
9th meeting participants
10th meeting participants
Contracting parties : Japan, Germany, Netherland, EC
NGOs, etc : OICA, GREWUS (Guest), EMEA (Guest)
9th Meeting : October 22-24, 2019 – Brussels
Small group drafting meeting
10th Meeting : January 28, 2020 – Geneva
Task force meeting
Contracting parties : Japan,
NGOs, etc : OICA, EMEA (Guest),

## Slide 3
Schedule of document submission to GRBP
TFRWS aimed to submit working document to GRBP in January, 2020 (GRBP #71).
Then, we decided to postpone submitting because validation of test method has not been conducted yet, and the information of limit value table to be discussed has not been provided enough by contracting parties.
However, as a chair, I propose to set our goal to submit it at January 2021 because it is too short to achieve our conclusion.
Status of discussion

## Slide 4
Part I
Step-wise self adjusting device : Validation test
Self adjusting device : Proposal of test method and validation test
Limit value : Calculated based on limit value of Part II
Effect of R28 : Modification of unsuitable sentences for RWS
Part II
Step-wise self adjusting device: Validation test
Self adjusting device : Proposal of test method and validation test
Limit value : Mode of sound level, necessity of limit value difference depending on sound type
Uncompleted items in a draft of new regulation

## Slide 5
Uncompleted item |  | TFRWS #10 GRBP #71 2020. 1 | TFRWS #11 2020. 5? | GRBP #72 +TFRWS ? 2020. 9 | TFRWS #12 2020. 11? | GRBP #73 2021. 1
Submitting document |  | Status report |  | Informal document |  | Working document
Part I | Limit value :Calculated based on part II limit value |  |  |  |  | 
 | Effect of R28 : Modification of unsuitable sentences for RWS |  |  |  |  | 
Part II | Limit value :Mode of sound level, necessity of limit value difference depending on sound type |  |  |  |  | 
New schedule of the draft with non-self-adjusting device only
：12 months extension
A test method for self-adjusting device has not been made, yet. TF group has already postponed our schedule twice. Therefore, it is appropriate to make a new regulation only for non-self-adjusting device (most of part are fixed) at first, then self-adjustable device shall be added to the new regulation as amendment.
Calculation

## Slide 6
New schedule of the draft including self-adjusting device
：18 months extension
Uncompleted item |  | TFRWS #10 GRBP #71 2020. 1 | TFRWS #11 2020. 5? | GRBP #72 +TFRWS ? 2020. 9 | TFRWS #12 2020. 11? | GRBP #73 2021. 1 | TFRWS #13 2020. 5? | GRBP #74 2021. 9
Submitting document |  | Status report |  | Status report |  | Informal document |  | Working document
Part I | Step-wise self adjusting device : Validation test |  |  |  |  |  |  | 
 | Self adjusting device : Proposal of test method and validation test |  |  |  |  |  |  | 
 | Limit value :Calculated based on part II limit value |  |  |  |  |  |  | 
 | Effect of R28 : Modification of unsuitable sentences for RWS |  |  |  |  |  |  | 
Part II | Step-wise self adjusting device : Validation test |  |  |  |  |  |  | 
 | Self adjusting device : Proposal of test method and validation test |  |  |  |  |  |  | 
 | Limit value :Mode of sound level, necessity of limit value difference depending on sound type |  |  |  |  |  |  | 
Proposal of test method
Validation test
Proposal of test method
Validation test
Waiting arrival of the device
Calculation
Waiting arrival of the device

## Slide 7
Requirement of warning sound
CLEPA proposed tonal sound should be limited from 700 Hz to 2800.
On the other hand, from 500 Hz to 4000Hz of tonal sound which is defined in South Korean domestic law, and Japanese current situation is same frequency range. Based on the information above, TF group agreed tonal sound should be from 500 Hz to 4000Hz.
TF group agreed sound emitting count per minute are 24-120.
Previously, table of limit value consists of 3 sound types (tonal sound, Broad band sound, 1/3 Octave band sound). After discussion in the group, TF group decided BBS and 1/3 octave band sound are same limit value.
Status of discussion

## Slide 8
Test method for self-adjusting device
The test method is being made, now. After completion, verification test will be conducted.
In part I test (component test), 4 different volume pink noise is proposed to be used.
In part II test (vehicle test), it is difficult to control BGN level, a realistic and an appropriate test method will be discussed.
Status of discussion

## Slide 9
Other safety device
From technical point of view, EC propose not to describe as rearward facing camera system or a detection system.
As a result of discussion, TF group decided other safety devices are indicated as "non-audible safety system". TFRWS will ask VRU-Proxi IWG above indication.
Status of discussion

## Slide 10
Coordination with GRSG and VRU-Proxi IWG
Switzerland reported last our status report (GRBP-70-24) to GRSG (October, 2020).
Following sentences were made by Switzerland and secretariat of GRSG
GRSG understand the need for a pause switch. However, it should not be active in every situation e.g. when a redundant safety system e.g. camera monitor system or detection system is not providing the sufficient safety.
GRSG considered as an example the case of a vehicle with a coupled trailer. If the vehicle with trailer is in reversing gear, the pause switch should be ineffective as the camera would not deliver necessary information to the driver.
GRSG recommends that the conditions shall be listed in the future regulation when the pause switch is effective or, if not possible, criteria shall be envisaged.

## Slide 11
Coordination with GRSG and VRU-Proxi IWG (con't)
Depending on suggestion by GRSG, the conditions when the pause switch is allowable or not, are summarized as follows.
Regarding trailer, it should be discussed that it is possible to make a system enable to judge whether the other safety device installed in the trailer is effective or not.

## Slide 12
The schedule will be decided at 28th, January 2020.
Schedule