## Sheet1
DEVP GTR Issues and status |  | for discussion at interim EVE teleconference on power determination, 12 March 2020 | yellow cells were most recently discussed
Issue | Sub issue | Description of issue | Resolution | Status | Relevant text
Alignment with GTR No. 15 | Measurement accuracy | Measurement accuracies under ISO 20762 may be different from GTR No 15 | Measurement accuracies have been reviewed, and aligned with GTR No. 15 or ISO 20762 as appropriate | Complete | GTR 5.2.1, E.1.1
| Definitions | Definitions under ISO 20762 and any new definitions should not conflict with those in GTR No 15 | Definitions have been reviewed, and aligned with GTR No 15 and Mutual Resolution No. 2. New definitions added only where necessary. | Complete | GTR 3.1 to 3.5, E.1.12
Agreement of results for TP1 and TP2 | Use of default K factors | Default K factors will not be equally accurate for every vehicle. This can lead to random variation between TP1 and TP2. | Require manufacturer to specify an accurate and verifiable K factor derived from an applicable test standard | Complete | GTR 6.1.1.2, E.1.2
| Use of dyno roller data for torque and speed (TP2) | Method not specified for determining tire losses when conducting TP2 using dyno roller data. Any method is likely to be inexact. Unclear how to measure and model tire slippage. | Require torque and speed sensors or hub dyno for TP2 | Complete | GTR 6.1.2.2, E.1.3
| Verification that engine is operating at R85 maximum power (TP1) | At constant engine speeds, MAP does not vary enough to be useful for confirming that R85 operating conditions were met. Fuel flow rate is more reliable. (VDA) | Require TP1 to collect fuel flow rate in addition to MAP. Onboard data may be used if accuracy is demonstrated. | Complete | E.1.4, GTR 6.1.2.1, 6.1.2
|  | When comparing measured MAP to R85, what tolerance is "close enough"? | Specify ± 2% tolerance (Japan recommendation at EVE31) | Complete | GTR 6.9.2, EVE-31-07e
|  | When comparing measured fuel flow rate to R85, what tolerance is "close enough"? | Specify ± 2% tolerance (Japan recommendation at EVE31) | Complete | GTR 6.9.2, EVE-31-07e
| Production engines may vary from R85 certification result (TP1) | Actual power of production engines may vary slightly from the accepted R85 result, contributing to error in TP1 | At type approval the allowed variation from declared value is 2 percent, vs. 5 percent at ISC (to allow for production variation or fuel differences). Because power determination is likely to take place at type approval, the variation that is encountered is likely to be only 2 percent. | No action needed
| TP1 higher than TP2 for power split HEV | VDA observation: For power split HEV, TP1 will always be higher than TP2 because TP2 accounts for losses in the series path but TP1 does not. | This is the result of inconsistency in the reference points implied by TP1 and TP2 for this architecture. It is resolved by defining the reference point consistently for both TP1 and TP2. | Complete | GTR Figure 9
| TP2 shows greater variability than TP1 | Some of the ISO and KATRI testing has suggested that TP2 may have more variation than TP1. | Accept the variation as a natural consequence of the fact that TP2 is calculated entirely from test measurements while TP1 is calculated in part from the fixed result of R85. | Complete
| Impact of accounting for 12V accessories | TP1 includes subtraction of an estimated power to DC-DC converter and 12V accessories (1.0 kW or measured value), while TP2 inherently accounts for the actual power. The size of the error amounts to a variation between TP1 and TP2. | Accept the small variation as an inevitable consequence of the difference between the two test procedures. | No action needed
Procedure | Gear shifting | If gear shifting is automatic but a manual gear shift is possible, is it permissible and under what circumstances? | Manufacturer specifies how to shift to achieve maximum power; gear must be accessible to normal driver and not a special or artificial mode | Complete | GTR 6.8.6
| Definition of 10-second window | Pressing the accelerator takes a finite amount of time. Does the 10-second window begin when the accelerator pedal begins to move, or when it has reached full depression? | Specify that the 10 second time window begins when pedal command has reached maximum (also, see below) | Complete | GTR 6.9.1
|  | What to do if an automatic gear shift occurs before the 10 second interval is complete | Specify that the 10 second time window begins when pedal command has reached maximum and gear position has stabilized. Gear must be accessible to normal driver and not a special or artificial mode | Complete | GTR 6.9.1
| Driver-selectable modes | If a vehicle has driver-selectable modes, which mode should the power test be conducted in? | Since the GTR is no longer limited only to WLTP downscaling and classification, no specific mode needs to be specified in the GTR. User should select the mode for which a system power rating is desired. The procedure should be robust enough to determine the system power when operating in any mode that the user of the GTR desires to test. (DG meeting, Geneva 2019) | Complete | GTR 6.8.5
| Slippage effect on vehicle behavior | Wheel slippage could affect shifting points or other vehicle behavior | Emphasize that measures should be taken to stabilize tire slippage that may occur during maximum power. | Complete | GTR 6.2.2
| Applicability of TP1 or TP2 based on powertrain characteristics | How to apply TP2 to planetary power split (e.g. THS) | Reference point is consistently defined to be at engine (R1) and MG (R2REESS). Applicability tests under 6.1.3 assign TP1 to this architecture. | Complete | GTR 6.1.3, Annex 1
|  | How to apply TP1 if the current from REESS powers more than one inverter/motor having different conversion efficiencies | If the electrical conversion efficiency on each path is not expected to be the same, then instrument the inputs to the inverters, or use verified onboard data, or provide a net K1 factor for the combined path | Complete | E.1.5, GTR 6.1.3.1
|  | How to generally and consistently determine applicability of TP1 or TP2 for any powertrain | Define the concept of "reference point". System power is the sum of power at the reference points. Provide guidelines for how to identify the reference points for any powertrain. Require that TP1 and TP2 both use the same reference points. TP1 or TP2 is applicable only if it can effectively convert the measured power to the power at the designated reference points. Provide rules of applicability (6.1.3) to help make the decision based on powertrain characteristics. | Complete | E.1.7, E.1.8, GTR Definitions at 3.5, GTR 6.1.2, 6.1.3, Annex 1
|  | How to clearly account for the power flow through the powertrain at maximum power, so that applicability can be reliably judged | Require manufacturer to provide hybrid power flow description | Complete | E.1.9, GTR 6.1.1.1
| How to test all-wheel drive vehicles | If there are two powered axles, and they are powered by a different set of components, how should the test be conducted? | Require each axle to be tested independently and simultaneously on a 4wd dynamometer or two hub dynos. | Complete | E.1.10, GTR 6.1
| REESS adjustment during test | Regeneration can be used to adjust SOC during test, but the allowable rate is not specified. Too high a rate might temporarily reduce the battery performance. | Specify monitoring and limitation of charge rate as recommended by manufacturer to avoid derating or heating of battery. | Complete | GTR 6.8.4
| Use of onboard data in place of instrumentation | Under what circumstances can onboard data be used where instrumentation is not practical or possible? | Adopted provisions of GTR No. 15 regarding use of onboard data if its accuracy is demonstrated to the responsible authority. | Complete | GTR 6.1.2
Repeatability | Same day repeatability (warm, within test) | The exact result of each test is likely to show some variation, but the reported result should be a single number. ISO 20762 does not specify repetition or averaging. | Specify five repetitions. System power is the average of the last four results. | Complete | E.1.6, GTR 6.8.7
|  | When the four results are averaged, how much variability is acceptable? | Each of the four results should not vary by more than 5 percent from the mean (similar to conformity of production variability of 5 percent established by R85). If not, repeat the tests, or seek approval of authority. | Drafted | GTR 6.9.1
| Day to day repeatability (cold) | The procedure should deliver the same results when tested on different days. | Validation results have not clearly indicated that this is a concern. | No action needed
Validation | Internal validation | Basic validation criteria that can be applied as part of the procedure | The implied drivetrain efficiency must be less than 100% | Complete | GTR 6.10, E.1.11
| External validation | Recommend how to validate manufacturer inputs (e.g. K factor) | Proposal: No action for now. In a future version, recommend: to validate a provided K factor for TP1 or TP2, if an applicable standard is not available and both TP1 and TP2 can be applied to the HEV architecture: perform both TPs, set TP1 = TP2 and solve for the missing K. Use engineering judgement to consider whether both K factors are reasonable for the conversion paths they represent. | No action needed | E.1.11
Manufacturer inputs | K1 factor for inverter+motor | Specify how a manufacturer should determine K1 for inverter/motor efficiency | Specify ISO 21782 or SAE J2907 | Complete | GTR 6.1.1.2
| K2 factor for gearbox | Specify how manufacturer should determine K2 for gearbox efficiency. No published standard is available that would apply to all gearbox implementations. | Specify that the gearbox efficiency is the output power divided by the input power, at the maximum power condition | Complete | GTR 6.1.1.2
ICE power correction | Reconstructing engine power for ICE power correction under TP2 | If a vehicle must be evaluated by TP2 instead of TP1 because the presence of multiple inverter/motor paths prevents estimation of motor power, it implies that ICE power correction also cannot be performed because it requires estimation of motor power. | This is likely to be a very rare situation. Provisions under 6.1.3.1 provide flexibilities for achieving TP1 in this case, and also use of onboard data is a possibility. Wait and see if it becomes a difficulty. | No action needed for now
Drafting group Oct 2019 | Conditioning cycle | Should there be a distinction between initial conditioning (warm up from cold) and within-procedure conditioning (to cool down to within nominal operating temperature). One could be dynamic while the other could be constant speed | Redrafted to make it clear that the goal is to stabilize temperatures, and the manufacturer or authority can modify the conditioning cycle as needed to achieve this. | Complete | GTR 6.8.3
| Gear shifting | Need clearer guidance on permissibility of any gear shifting, e.g. manual shift - meaning of "ordinary driving" | Redrafted to make it clear that a gear shift is permissible but only if accessible to an ordinary driver | Complete | GTR 6.8.5
| Default accessory load for TP1 | Is 1.0 kW still representative for P(dcdc)? Elena will look at JRC data | JRC data indicates that there is some variation, but not enough data at this time to justify a change from 1.0 kW. | No action needed for now | GTR 6.9.2
| Hybrid power compensation | Study the fact that the presence of electrical hybrid power compensation could possibly remove the need for engine power correction, and how to represent in the GTR | Uncertain whether any vehicles in the market are doing this. Not likely that it can replace the need for engine power compensation. Redrafted to be same as ISO 20762, and additional requirement that if there is electrical power compensation, the amount of compensation shall be deducted from the total after the correction is performed. | Complete | GTR 6.9.3.3
Second phase validation | Air conditioning used intermittently to cool battery, motor, or power electronics | Some vehicles use air conditioning unit to cool powertrain and will draw significant power when cooling is needed; operation may vary between tests; may be difficult to measure electrically. | HV power draw of compressor is accounted for or estimated as Paux. Adequate warm up should result in relatively stable cycling. Averaging last four of five repetitions should reduce the effect of variation. | No action needed for now
| Dynamometer speed control | Possible dynamometer speed oscillation at beginning of power command can affect peak power result or judgement as to where the 10-second window should begin | Propose: no action for now. We already have requirement for speed accuracy of 0.2 kph in 5.2.1 which should apply to potential osciallation. We should not delay the beginning of the 10-second window to accommodate oscillation as this could affect the peak power result. | Drafted | (no specific text)