## Feuil1
Macro-Gantt in case of scenario 1b
Scenario 1b = Oct 2020 - "Draft" Working Document submittal for Jan 2021 GRBP. Jan 2021 - Amend the "Draft" Working Document by an Informal Document
Scenario 3 (informal doc Jan 2021, working doc Sept 2021) is still a possible option
| 2019 |  |  | 2020 | [11 empty] | 2021 | [11 empty] | 2022 | [11 empty] | 2023 | [11 empty] | 2024 | [11 empty] | 2025 | [11 empty] | 2026
| O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D
1.a) Define candidates list for screening test plan | bar: 2019 N to 2019 D
1.b) Define candidates list for analytical test plans | bar: 2019 N to 2019 D
1.c) Built a test plan matrix: candidate x test method x participant | bar: 2019 D to 2020 J
2.a) Buy tires - and deliver them to buffing centers | bar: 2020 F to 2020 M
2.b) Deliver SRTTs them to participants | bar: 2020 F
2.c) Deliver SRTTs to buffing centers | bar: 2020 M
3) Buff tires | bar: 2020 A to 2020 A
4) Test tires | bar: 2020 J to 2020 N
5) Share results & analyze | bar: 2020 A to 2021 J
6) Drafting the proposal | bar: 2020 J to 2020 D
Informal document for Sept-2020 GRBP | bar: 2020 A
Working document submittal for Jan-2021 GRBP | bar: 2020 O
Informal document supplementing the working document | bar: 2021 J
WP29 adoption | bar: 2021 J
Entry into force | bar: 2021 D
Deadlines from Regulation (EU) 2019/2144
UN→EU: expected GRBP/WP29 adoption for worn C1 tyres | 2021 J: GRBP; 2021 J: WP29
UN→EU: expected GRBP/WP29 adoption for worn C2, C3 tyres | 2021 S: GRBP; 2022 M: WP29
Committee (MS vote) estimated date for worn C1, C2, C3 tyres | bar: 2022 O to 2022 N
Official Journal (art.5 and 4(7)) for worn C1, C2, C3 tyres | bar: 2023 A
Application of new regulation for worn C1, C2, C3 tyres | 2024 J: New Types; 2026 J: All Types
final agreement on testplan gantt
gantt for documentation
adoption / EIF / application