## Sheet1
| TF of RWS : Remaining Issue items and time plan |  |  |  | 11th TF of RWS JASIC
No | Group | Item | Detail or action | Responsibility | Schedule
1 | Research | validation test result | Review of each measurement results. Analyze to the results |  | ~OCT 2020
2 |  | Necessity of High mode | Clarify situation about high mode in Europe
3 | Non self adjusting | Limit value (Based on JP & DE proposal) | Normal mode : 58~78dB Low mode : [43]~58dB |  | ~OCT 2020
4 |  | Test procedures of component test | Detail checking
5 |  | Test procedures of vehicle test | Feedback from the validation test if needed
6 |  | Others
7 | Self adjusting | Limit value |  |  | ?
8 |  | Test procedures of component test | Make clear how to test/judgement
9 |  | Test procedures of vehicle test | Make clear how to test/judgement
10 |  | Background noise level on the device | Difference between background noise level and reference noise level
11 |  | Switching time | Technical data to dicide appropriate switching time
12 |  | Threshold values | Technical validity of threshold values
13 |  | Others | Durability of reference micro
14 | Drafting | Definition of mandatory/optional of each mode | TF agreed as follows. It should be reflected in the draft. Mandatory : Normal mode Optional : Other mode |  | ~NOV 2020
15 |  | Deferency between each mode | Define of difference level
16 |  | Define to the test procedures of self adjusting system
17 |  | Detail check
Others